## Landless
S. N. | District | AS On 20th Nov | [5 empty] | As On 7th Dec |  |  |  |  | Achivement
|  | Landless beneficiaries in PWL | Landless Beneficiaries Provided Land |  |  |  |  | Landless Beneficiaries provided Land
|  |  | PDU | Free Govt. land | Encroachment Regularization | Other | Total | PDU | Free Govt. Land | Encroachment Regularisation | Other | Total
1 | AMRAVATI | 14998 | 223 | 0 | 0 | 0 | 223 | 267 | 3295 | 3396 | 0 | 6958 | 6735
2 | BULDHANA | 4942 | 0 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 257 | 257
3 | WASHIM | 574 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 470 | 0 | 494 | 494
4 | AKOLA | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | YAVATMAL | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NAGPUR | 10344 | 26 | 0 | 0 | 0 | 26 | 49 | 343 | 0 | 0 | 392 | 366
7 | BHANDARA | 4626 | 0 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 257 | 257
8 | CHANDRAPUR | 1300 | 16 | 0 | 0 | 0 | 16 | 44 | 0 | 114 | 0 | 158 | 142
9 | WARDHA | 1129 | 75 | 0 | 0 | 0 | 75 | 91 | 42 | 0 | 0 | 133 | 58
10 | GONDIA | 262 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
11 | GADCHIROLI | 17 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0
12 | AHMEDNAGAR | 9281 | 203 | 0 | 0 | 0 | 203 | 68 | 158 | 0 | 0 | 226 | 23
13 | JALGAON | 9718 | 4932 | 0 | 0 | 0 | 4932 | 776 | 1122 | 0 | 5813 | 7711 | 2779
14 | NASHIK | 611 | 81 | 0 | 0 | 0 | 81 | 81 | 0 | 0 | 0 | 81 | 0
15 | NANDURBAR | 98 | 0 | 0 | 0 | 0 | 0 | 49 | 343 | 0 | 0 | 392 | 392
16 | DHULE | 37 | 37 | 0 | 0 | 0 | 37 | 41 | 0 | 0 | 0 | 41 | 4
17 | SOLAPUR | 5903 | 54 | 0 | 0 | 0 | 54 | 77 | 484 | 0 | 0 | 561 | 507
18 | KOLHAPUR | 1470 | 17 | 0 | 0 | 0 | 17 | 35 | 0 | 0 | 0 | 35 | 18
19 | SATARA | 1562 | 9 | 6 | 10 | 0 | 25 | 9 | 6 | 10 | 0 | 25 | 0
20 | PUNE | 1103 | 33 | 0 | 0 | 0 | 33 | 46 | 923 | 0 | 0 | 969 | 936
21 | SANGLI | 567 | 51 | 0 | 0 | 0 | 51 | 38 | 60 | 0 | 0 | 98 | 47
22 | JALNA | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | AURANGABAD | 615 | 137 | 0 | 0 | 0 | 137 | 68 | 158 | 0 | 0 | 226 | 89
24 | LATUR | 410 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 5 | 0
25 | HINGOLI | 394 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 125 | 125
26 | OSMANABAD | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | NANDED | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | BEED | 110 | 88 | 0 | 0 | 0 | 88 | 88 | 0 | 0 | 0 | 88 | 0
29 | PARBHANI | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | RAIGAD | 445 | 17 | 0 | 0 | 0 | 17 | 17 | 0 | 0 | 0 | 17 | 0
31 | SINDHUDURG | 392 | 11 | 0 | 0 | 0 | 11 | 57 | 0 | 0 | 0 | 57 | 46
32 | RATNAGIRI | 219 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 0
33 | THANE | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19
34 | PALGHAR | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 73052 | 9168 | 0 | 0 | 0 | 9168 | 2573 | 6934 | 3990 | 5832 | 19329 | 13295

## PMAY-G
31 | THANE | 7395 | 6483 | 6492 | 9 | 903 | 6221 | 6221 | 0 | 271 | 5494 | 5494 | 0 | 1901
29 | SINDHUDURG | 4947 | 3143 | 3143 | 0 | 1804 | 2895 | 2901 | 6 | 242 | 2520 | 2520 | 0 | 2427
21 | OSMANABAD | 6632 | 4909 | 4910 | 1 | 1722 | 3777 | 3882 | 105 | 1028 | 3145 | 3145 | 0 | 3487
23 | PARBHANI | 7603 | 6409 | 6409 | 0 | 1194 | 4760 | 4775 | 15 | 1634 | 3915 | 3916 | 1 | 3687
25 | RAIGAD | 9566 | 7298 | 7295 | -3 | 2271 | 6615 | 6682 | 67 | 613 | 5868 | 5874 | 6 | 3692
26 | RATNAGIRI | 8100 | 6084 | 6084 | 0 | 2016 | 4203 | 4210 | 7 | 1874 | 3851 | 3852 | 1 | 4248
16 | LATUR | 11302 | 7495 | 7495 | 0 | 3807 | 7236 | 7236 | 0 | 259 | 6367 | 6368 | 1 | 4934
12 | HINGOLI | 11335 | 7983 | 7983 | 0 | 3352 | 7205 | 7244 | 39 | 739 | 5975 | 5978 | 3 | 5357
33 | WASHIM | 11091 | 6512 | 6512 | 0 | 4579 | 6396 | 6396 | 0 | 116 | 5227 | 5229 | 2 | 5862
22 | PALGHAR | 26966 | 25678 | 25687 | 9 | 1279 | 24849 | 24855 | 6 | 832 | 20740 | 20796 | 56 | 6170
14 | JALNA | 13465 | 8191 | 8191 | 0 | 5274 | 7547 | 7557 | 10 | 634 | 5979 | 5983 | 4 | 7482
28 | SATARA | 14166 | 11022 | 11046 | 24 | 3120 | 7481 | 7493 | 12 | 3553 | 6270 | 6275 | 5 | 7891
15 | KOLHAPUR | 17047 | 12671 | 12697 | 26 | 4350 | 9720 | 9730 | 10 | 2967 | 7885 | 7886 | 1 | 9161
32 | WARDHA | 17575 | 10590 | 10816 | 226 | 6759 | 9341 | 9357 | 16 | 1459 | 7644 | 7648 | 4 | 9927
5 | BEED | 20320 | 15066 | 15630 | 564 | 4690 | 11172 | 11172 | 0 | 4458 | 8896 | 8900 | 4 | 11420
4 | AURANGABAD | 23273 | 21630 | 21630 | 0 | 1643 | 14030 | 14333 | 303 | 7297 | 10943 | 10943 | 0 | 12330
10 | GADCHIROLI | 23746 | 20420 | 20419 | -1 | 3327 | 16026 | 16076 | 50 | 4343 | 11083 | 11089 | 6 | 12657
24 | PUNE | 21818 | 12882 | 12960 | 78 | 8858 | 11509 | 11523 | 14 | 1437 | 8842 | 8844 | 2 | 12974
27 | SANGLI | 22172 | 12628 | 12879 | 251 | 9293 | 11321 | 11341 | 20 | 1538 | 8751 | 8775 | 24 | 13397
7 | BULDHANA | 30604 | 19708 | 19708 | 0 | 10896 | 17702 | 17708 | 6 | 2000 | 14312 | 14319 | 7 | 16285
8 | CHANDRAPUR | 32694 | 27450 | 27463 | 13 | 5231 | 20473 | 21162 | 689 | 6301 | 15781 | 15787 | 6 | 16907
9 | DHULE | 52614 | 44325 | 44325 | 0 | 8289 | 37261 | 37636 | 375 | 6689 | 29937 | 29954 | 17 | 22660
20 | NASHIK | 72630 | 67213 | 67224 | 11 | 5406 | 60129 | 61029 | 900 | 6195 | 48230 | 48284 | 54 | 24346
2 | AKOLA | 47181 | 31555 | 31555 | 0 | 15626 | 26354 | 26560 | 206 | 4995 | 19787 | 19815 | 28 | 27366
30 | SOLAPUR | 49500 | 32218 | 32656 | 438 | 16844 | 22534 | 22538 | 4 | 10118 | 18596 | 18607 | 11 | 30893
17 | NAGPUR | 45792 | 31079 | 31515 | 436 | 14277 | 19527 | 19618 | 91 | 11897 | 14596 | 14604 | 8 | 31188
18 | NANDED | 50791 | 40000 | 40000 | 0 | 10791 | 26314 | 26375 | 61 | 13625 | 17960 | 17967 | 7 | 32824
1 | AHMEDNAGAR | 56134 | 35623 | 35623 | 0 | 20511 | 29759 | 29761 | 2 | 5862 | 21135 | 21176 | 41 | 34958
6 | BHANDARA | 63597 | 36473 | 36473 | 0 | 27124 | 28463 | 28675 | 212 | 7798 | 20030 | 20080 | 50 | 43517
13 | JALGAON | 75723 | 47379 | 47383 | 4 | 28340 | 37905 | 38027 | 122 | 9356 | 29078 | 29091 | 13 | 46632
19 | NANDURBAR | 111956 | 98262 | 98261 | -1 | 13695 | 90848 | 91220 | 372 | 7041 | 62317 | 62342 | 25 | 49614
3 | AMRAVATI | 93272 | 54277 | 54670 | 393 | 38602 | 48344 | 48391 | 47 | 6279 | 38107 | 38121 | 14 | 55151
11 | GONDIA | 92862 | 69416 | 69752 | 336 | 23110 | 41693 | 42251 | 558 | 27501 | 24861 | 24883 | 22 | 67979
Cummulative PMAY-G Online Progress Report From 17th Dec 2020 | [13 empty] | Remaining
SNo | District Name | Target | Sanctions Out of GEO Tagged |  |  |  | 1st Installment |  |  |  | Completion |  |  | #VALUE!
|  |  | As On 16th Nov | As On 17th Dec | Achievement | Remaining | As On 16th Dec | As On 17th Dec | Achievement | Remaining | As On 16th Nov | As On 17th Dec | Achievement | #VALUE!
34 | YAVATMAL | 41521 | 31766 | 31766 | 0 | 9755 | 25176 | 25179 | 3 | 6587 | 19828 | 19835 | 7
| Total | 1195390 | 873838 | 876652 | 2814 | 318738 | 704786 | 709114 | 4328 | 167538 | 533950 | 534380 | 430

## State Scheme
Yesterday 16.12.2020 | [8 empty] | Today 17.12.2020
. |  |  |  |  | Installment |  |  |  | . |  |  |  |  | Installment |  |  |  | 29 | SINDHUDURG | 1851 | 0 | 0 | 0 | 1851 | Installment | 1526 | #VALUE! | -1526 | 0 | 0 | 0 | 1851
[18 empty] | 31 | THANE | 3524 | 0 | 0 | 0 | 3524 | 0 | 3237 | -3237 | -3237 | 0 | 0 | 0 | 3524
#SNo | District Name | Target fixed by States | Sanctions Out of GEO Tagged | Remaining Sanction | 1st | Remaining 1st Installment | Completed | Incompleted | #SNo | District Name | Target fixed by States | Sanctions Out of GEO Tagged | Remaining Sanction | 1st | Remaining 1st Installment | Completed | Incompleted | 25 | RAIGAD | 3833 | Sanctions Out of GEO Tagged | Sanctions Out of GEO Tagged | #VALUE! | #VALUE! | 1st | 3389 | #VALUE! | #VALUE! | Completed | Completed | #VALUE! | #VALUE!
1 | AHMEDNAGAR | 30450 | 28079 | 2371 | 23691 | 4388 | 15731 | 14719 | 1 | AHMEDNAGAR | 30450 | 28085 | 2365 | 23691 | 4394 | 15756 | 14694 | 26 | RATNAGIRI | 5864 | 28079 | 28085 | 6 | -22221 | 23691 | 5498 | 18193 | 22587 | 15731 | 15756 | 25 | -9892
2 | AKOLA | 14198 | 13397 | 801 | 9219 | 4178 | 5896 | 8302 | 2 | AKOLA | 14198 | 13397 | 801 | 9221 | 4176 | 5908 | 8290 | 27 | SANGLI | 7082 | 13397 | 13397 | 0 | -6315 | 9219 | 5311 | 3908 | 8086 | 5896 | 5908 | 12 | 1174
3 | AMRAVATI | 14486 | 13892 | 594 | 10719 | 3173 | 8115 | 6371 | 3 | AMRAVATI | 14486 | 13893 | 593 | 10719 | 3174 | 8121 | 6365 | 22 | PALGHAR | 6455 | 13892 | 13893 | 1 | -7438 | 10719 | 5490 | 5229 | 8403 | 8115 | 8121 | 6 | -1666
4 | AURANGABAD | 17770 | 16446 | 1324 | 8518 | 7928 | 6093 | 11677 | 4 | AURANGABAD | 17770 | 16446 | 1324 | 8518 | 7928 | 6100 | 11670 | 28 | SATARA | 9559 | 16446 | 16446 | 0 | -6887 | 8518 | 7709 | 809 | 8737 | 6093 | 6100 | 7 | 3459
5 | BEED | 13236 | 9031 | 4205 | 8683 | 348 | 6631 | 6605 | 5 | BEED | 13236 | 9031 | 4205 | 8683 | 348 | 6631 | 6605 | 17 | NAGPUR | 9482 | 9031 | 9031 | 0 | 451 | 8683 | 8022 | 661 | 1009 | 6631 | 6631 | 0 | 2851
6 | BHANDARA | 15386 | 14315 | 1071 | 12599 | 1716 | 7158 | 8228 | 6 | BHANDARA | 15386 | 14315 | 1071 | 12599 | 1716 | 7163 | 8223 | 15 | KOLHAPUR | 10935 | 14315 | 14315 | 0 | -3380 | 12599 | 8891 | 3708 | 5424 | 7158 | 7163 | 5 | 3772
7 | BULDHANA | 12190 | 11995 | 195 | 9206 | 2789 | 7678 | 4512 | 7 | BULDHANA | 12190 | 11995 | 195 | 9206 | 2789 | 7686 | 4504 | 12 | HINGOLI | 9745 | 11995 | 11995 | 0 | -2250 | 9206 | 7730 | 1476 | 4265 | 7678 | 7686 | 8 | 2059
8 | CHANDRAPUR | 24728 | 16600 | 8128 | 15277 | 1323 | 7890 | 16838 | 8 | CHANDRAPUR | 24728 | 16603 | 8125 | 15303 | 1300 | 7924 | 16804 | 32 | WARDHA | 8310 | 16600 | 16603 | 3 | -8293 | 15277 | 7755 | 7522 | 8848 | 7890 | 7924 | 34 | 386
9 | DHULE | 12351 | 11917 | 434 | 10635 | 1282 | 7781 | 4570 | 9 | DHULE | 12351 | 11917 | 434 | 10635 | 1282 | 7794 | 4557 | 33 | WASHIM | 7712 | 11917 | 11917 | 0 | -4205 | 10635 | 5518 | 5117 | 6399 | 7781 | 7794 | 13 | -82
10 | GADCHIROLI | 11477 | 10105 | 1372 | 8728 | 1377 | 5306 | 6171 | 10 | GADCHIROLI | 11477 | 10105 | 1372 | 8728 | 1377 | 5314 | 6163 | 14 | JALNA | 7135 | 10105 | 10105 | 0 | -2970 | 8728 | 4945 | 3783 | 5160 | 5306 | 5314 | 8 | 1821
11 | GONDIA | 13480 | 9360 | 4120 | 7932 | 1428 | 4978 | 8502 | 11 | GONDIA | 13480 | 9364 | 4116 | 7939 | 1425 | 4989 | 8491 | 24 | PUNE | 10457 | 9360 | 9364 | 4 | 1093 | 7932 | 8069 | -137 | 1295 | 4978 | 4989 | 11 | 5468
12 | HINGOLI | 9745 | 8365 | 1380 | 7730 | 635 | 6176 | 3569 | 12 | HINGOLI | 9745 | 8365 | 1380 | 7730 | 635 | 6184 | 3561 | 19 | NANDURBAR | 10307 | 8365 | 8365 | 0 | 1942 | 7730 | 9191 | -1461 | -826 | 6176 | 6184 | 8 | 4123
13 | JALGAON | 17383 | 16095 | 1288 | 12308 | 3787 | 8982 | 8401 | 13 | JALGAON | 17383 | 16095 | 1288 | 12308 | 3787 | 8990 | 8393 | 30 | SOLAPUR | 15433 | 16095 | 16095 | 0 | -662 | 12308 | 12784 | -476 | 3311 | 8982 | 8990 | 8 | 6443
14 | JALNA | 7135 | 5123 | 2012 | 4949 | 174 | 3207 | 3928 | 14 | JALNA | 7135 | 5123 | 2012 | 4950 | 173 | 3210 | 3925 | 7 | BULDHANA | 12190 | 5123 | 5123 | 0 | 7067 | 4949 | 9203 | -4254 | -4080 | 3207 | 3210 | 3 | 8980
15 | KOLHAPUR | 10935 | 10836 | 99 | 8891 | 1945 | 7802 | 3133 | 15 | KOLHAPUR | 10935 | 10836 | 99 | 8891 | 1945 | 7814 | 3121 | 9 | DHULE | 12351 | 10836 | 10836 | 0 | 1515 | 8891 | 10635 | -1744 | 201 | 7802 | 7814 | 12 | 4537
16 | LATUR | 19992 | 16004 | 3988 | 13389 | 2615 | 10458 | 9534 | 16 | LATUR | 19992 | 16004 | 3988 | 13389 | 2615 | 10458 | 9534 | 23 | PARBHANI | 14543 | 16004 | 16004 | 0 | -1461 | 13389 | 10918 | 2471 | 5086 | 10458 | 10458 | 0 | 4085
17 | NAGPUR | 9482 | 9132 | 350 | 8030 | 1102 | 6525 | 2957 | 17 | NAGPUR | 9482 | 9132 | 350 | 8032 | 1100 | 6525 | 2957 | 10 | GADCHIROLI | 11477 | 9132 | 9132 | 0 | 2345 | 8030 | 8728 | -698 | 404 | 6525 | 6525 | 0 | 4952
18 | NANDED | 17863 | 10056 | 7807 | 9110 | 946 | 5886 | 11977 | 18 | NANDED | 17863 | 10056 | 7807 | 9110 | 946 | 5889 | 11974 | 3 | AMRAVATI | 14486 | 10056 | 10056 | 0 | 4430 | 9110 | 10716 | -1606 | -660 | 5886 | 5889 | 3 | 8597
19 | NANDURBAR | 10307 | 9835 | 472 | 9191 | 644 | 6106 | 4201 | 19 | NANDURBAR | 10307 | 9835 | 472 | 9191 | 644 | 6106 | 4201 | 5 | BEED | 13236 | 9835 | 9835 | 0 | 3401 | 9191 | 8683 | 508 | 1152 | 6106 | 6106 | 0 | 7130
20 | NASHIK | 19111 | 17939 | 1172 | 14523 | 3416 | 9131 | 9980 | 20 | NASHIK | 19111 | 17941 | 1170 | 14523 | 3418 | 9142 | 9969 | 6 | BHANDARA | 15386 | 17939 | 17941 | 2 | -2555 | 14523 | 12577 | 1946 | 5364 | 9131 | 9142 | 11 | 6244
21 | OSMANABAD | 15251 | 8387 | 6864 | 6003 | 2384 | 4409 | 10842 | 21 | OSMANABAD | 15251 | 8387 | 6864 | 6003 | 2384 | 4409 | 10842 | 2 | AKOLA | 14198 | 8387 | 8387 | 0 | 5811 | 6003 | 9213 | -3210 | -826 | 4409 | 4409 | 0 | 9789
22 | PALGHAR | 6455 | 5806 | 649 | 5495 | 311 | 3915 | 2540 | 22 | PALGHAR | 6455 | 5806 | 649 | 5495 | 311 | 3921 | 2534 | 13 | JALGAON | 17383 | 5806 | 5806 | 0 | 11577 | 5495 | 12264 | -6769 | -6458 | 3915 | 3921 | 6 | 13462
23 | PARBHANI | 14543 | 12290 | 2253 | 10920 | 1370 | 9079 | 5464 | 23 | PARBHANI | 14543 | 12290 | 2253 | 10920 | 1370 | 9093 | 5450 | 11 | GONDIA | 13480 | 12290 | 12290 | 0 | 1190 | 10920 | 7929 | 2991 | 4361 | 9079 | 9093 | 14 | 4387
24 | PUNE | 10457 | 8727 | 1730 | 8132 | 595 | 6345 | 4112 | 24 | PUNE | 10457 | 8727 | 1730 | 8132 | 595 | 6351 | 4106 | 16 | LATUR | 19992 | 8727 | 8727 | 0 | 11265 | 8132 | 13389 | -5257 | -4662 | 6345 | 6351 | 6 | 13641
25 | RAIGAD | 3833 | 3803 | 30 | 3393 | 410 | 2966 | 867 | 25 | RAIGAD | 3833 | 3803 | 30 | 3393 | 410 | 2973 | 860 | 34 | YAVATMAL | 19265 | 3803 | 3803 | 0 | 15462 | 3393 | 16474 | -13081 | -12671 | 2966 | 2973 | 7 | 16292
26 | RATNAGIRI | 5864 | 5858 | 6 | 5498 | 360 | 4568 | 1296 | 26 | RATNAGIRI | 5864 | 5858 | 6 | 5498 | 360 | 4568 | 1296 | 20 | NASHIK | 19111 | 5858 | 5858 | 0 | 13253 | 5498 | 14520 | -9022 | -8662 | 4568 | 4568 | 0 | 14543
27 | SANGLI | 7082 | 6229 | 853 | 5311 | 918 | 4603 | 2479 | 27 | SANGLI | 7082 | 6234 | 848 | 5311 | 923 | 4604 | 2478 | 21 | OSMANABAD | 15251 | 6229 | 6234 | 5 | 9017 | 5311 | 5999 | -688 | 235 | 4603 | 4604 | 1 | 10647
28 | SATARA | 9559 | 9505 | 54 | 7709 | 1796 | 6712 | 2847 | 28 | SATARA | 9559 | 9505 | 54 | 7709 | 1796 | 6733 | 2826 | 4 | AURANGABAD | 17770 | 9505 | 9505 | 0 | 8265 | 7709 | 8507 | -798 | 998 | 6712 | 6733 | 21 | 11037
29 | SINDHUDURG | 1851 | 1834 | 17 | 1526 | 308 | 1449 | 402 | 29 | SINDHUDURG | 1851 | 1834 | 17 | 1526 | 308 | 1450 | 401 | 18 | NANDED | 17863 | 1834 | 1834 | 0 | 16029 | 1526 | 9110 | -7584 | -7276 | 1449 | 1450 | 1 | 16413
30 | SOLAPUR | 15433 | 15044 | 389 | 12784 | 2260 | 11052 | 4381 | 30 | SOLAPUR | 15433 | 15044 | 389 | 12784 | 2260 | 11055 | 4378 | 1 | AHMEDNAGAR | 30450 | 15044 | 15044 | 0 | 15406 | 12784 | 12784 | 0 | 2260 | 11052 | 11055 | 3 | 19395
31 | THANE | 3524 | 3264 | 260 | 3237 | 27 | 2701 | 823 | 31 | THANE | 3524 | 3264 | 260 | 3237 | 27 | 2701 | 823 | 8 | CHANDRAPUR | 24728 | 3264 | 3264 | 0 | 21464 | 3237 | 15262 | -12025 | -11998 | 2701 | 2701 | 0 | 22027
32 | WARDHA | 8310 | 8297 | 13 | 7757 | 540 | 4686 | 3624 | 32 | WARDHA | 8310 | 8297 | 13 | 7757 | 540 | 4701 | 3609 |  | Total | 430844 | 8297 | 8297 | 0 | 422547 | 283336 | 301976 | -18640 | -293679 | 4686 | 4701 | 15 | 426143
33 | WASHIM | 7712 | 7698 | 14 | 5521 | 2177 | 3849 | 3863 | 33 | WASHIM | 7712 | 7698 | 14 | 5521 | 2177 | 3849 | 3863 | #SNo | District Name | Target fixed by States | 16.12.2020 | 17.12.2020 | Achievement | Remaining Sanction | 16.12.2020 | 17.12.2020 | Achievement | Yet to give 1st Inst | 16.12.2020 | 17.12.2020 | Achievement | Incompleted
34 | YAVATMAL | 19265 | 18946 | 319 | 16474 | 2472 | 9619 | 9646 | 34 | YAVATMAL | 19265 | 18946 | 319 | 16474 | 2472 | 9636 | 9629 | State Scheme Report Cumulative
| Total | 430844 | 374210 | 56634 | 313088 | 61122 | 223483 | 207361 |  | Total | 430844 | 374231 | 56613 | 313126 | 61105 | 223748 | 207096 |  |  |  | Sanctions Out of GEO Tagged |  |  |  | 1st Installment |  |  |  | Completion

## Delayed Houses
SNo | District Name | Houses not completed even after 12 Months after receiving First Installment(16/12/2020) | Houses not completed even after 12 Months after receiving First Installment(17/12/2020) | Achievement
| Total | 92988 | 92767 | -221
19 | NANDURBAR | 15083 | 15072 | -11
3 | AMRAVATI | 6563 | 6556 | -7
1 | AHMEDNAGAR | 6202 | 6167 | -35 | Sr. | District | Target | Sanction | Sanction % | Remaining | State Rank
20 | NASHIK | 5831 | 5794 | -37 | No. |  |  |  |  | Sanction
18 | NANDED | 5540 | 5538 | -2 | 1 | NASHIK | 72630 | 67238 | 92.58 | 5392
13 | JALGAON | 5350 | 5344 | -6 | 2 | DHULE | 52614 | 44327 | 84.25 | 8287
9 | DHULE | 4928 | 4916 | -12 | 3 | NANDURBAR | 111956 | 98391 | 87.88 | 13565
2 | AKOLA | 4576 | 4554 | -22 | 4 | AHMEDNAGAR | 56134 | 35623 | 63.46 | 20511
34 | YAVATMAL | 3969 | 3965 | -4 | 5 | JALGAON | 75723 | 47399 | 62.6 | 28324
30 | SOLAPUR | 3276 | 3267 | -9
10 | GADCHIROLI | 3185 | 3182 | -3
11 | GONDIA | 2921 | 2911 | -10
6 | BHANDARA | 2704 | 2691 | -13
8 | CHANDRAPUR | 2570 | 2564 | -6
7 | BULDHANA | 2226 | 2224 | -2
4 | AURANGABAD | 2023 | 2023 | 0
27 | SANGLI | 1724 | 1715 | -9
24 | PUNE | 1660 | 1658 | -2
17 | NAGPUR | 1570 | 1568 | -2
22 | PALGHAR | 1518 | 1514 | -4
5 | BEED | 1259 | 1258 | -1
32 | WARDHA | 1166 | 1164 | -2
15 | KOLHAPUR | 1074 | 1068 | -6
33 | WASHIM | 934 | 933 | -1
14 | JALNA | 853 | 853 | 0
28 | SATARA | 839 | 835 | -4
16 | LATUR | 670 | 669 | -1
23 | PARBHANI | 579 | 578 | -1
31 | THANE | 527 | 527 | 0
25 | RAIGAD | 485 | 479 | -6
21 | OSMANABAD | 438 | 438 | 0
12 | HINGOLI | 434 | 433 | -1
26 | RATNAGIRI | 186 | 184 | -2
29 | SINDHUDURG | 125 | 125 | 0

## Financial Completion
PMAY-G District Financial Incomplete Houses |  |  |  |  | State Schemes District Financial Incomplete Houses
Sr. No. | District | Financial Incomplete Houses as on 17th Dec | Financial Incomplete Houses as on 18th Dec | Achivement From 17th to 18th Dec | 29 | SINDHUDURG | 783 |  | -783
| Grand Total | 368271 |  | 368271 | 31 | THANE | 2143 |  | -2143
19 | NANDURBAR | 46692 |  | 46692 | 14 | JALNA | 2186 |  | -2186
20 | NASHIK | 38352 |  | 38352 | 26 | RATNAGIRI | 2301 |  | -2301
9 | DHULE | 24085 |  | 24085 | 25 | RAIGAD | 2337 |  | -2337
3 | AMRAVATI | 22833 |  | 22833 | 11 | GONDIA | 2462 |  | -2462
13 | JALGAON | 21284 |  | 21284 | 33 | WASHIM | 2538 |  | -2538 | Sr.No. | District | Target | Sanction | Completion | Financial Incomplete Houses | State Rank
11 | GONDIA | 15400 |  | 15400 | 6 | BHANDARA | 2620 |  | -2620 | 1 | NANDURBAR | 10307 | 9835 | 6101 | 4270 | 18
22 | PALGHAR | 14404 |  | 14404 | 22 | PALGHAR | 2879 |  | -2879 | 2 | NASHIK | 19111 | 11917 | 7794 | 6337 | 29
1 | AHMEDNAGAR | 13886 |  | 13886 | 27 | SANGLI | 3122 |  | -3122 | 3 | JALGAON | 17342 | 16095 | 8990 | 6326 | 27
30 | SOLAPUR | 13742 |  | 13742 | 21 | OSMANABAD | 3313 |  | -3313 | 4 | DHULE | 12351 | 17941 | 9142 | 5292 | 26
6 | BHANDARA | 12894 |  | 12894 | 17 | NAGPUR | 3319 |  | -3319 | 5 | AHMEDNAGAR | 30430 | 28085 | 15756 | 10318 | 34
34 | YAVATMAL | 11757 |  | 11757 | 5 | BEED | 3853 |  | -3853 |  | Total | 89541 | 83873 | 47783 | 32543
2 | AKOLA | 11569 |  | 11569 | 32 | WARDHA | 3897 |  | -3897
18 | NANDED | 11482 |  | 11482 | 2 | AKOLA | 3905 |  | -3905
8 | CHANDRAPUR | 10083 |  | 10083 | 28 | SATARA | 4036 |  | -4036
7 | BULDHANA | 9235 |  | 9235 | 4 | AURANGABAD | 4222 |  | -4222
17 | NAGPUR | 8134 |  | 8134 | 19 | NANDURBAR | 4270 |  | -4270
4 | AURANGABAD | 6663 |  | 6663 | 23 | PARBHANI | 4372 |  | -4372
24 | PUNE | 6477 |  | 6477 | 10 | GADCHIROLI | 4468 |  | -4468
5 | BEED | 6462 |  | 6462 | 24 | PUNE | 4742 |  | -4742
27 | SANGLI | 6207 |  | 6207 | 18 | NANDED | 4946 |  | -4946
10 | GADCHIROLI | 6138 |  | 6138 | 15 | KOLHAPUR | 5049 |  | -5049
15 | KOLHAPUR | 6034 |  | 6034 | 9 | DHULE | 5292 |  | -5292
28 | SATARA | 5138 |  | 5138 | 7 | BULDHANA | 5330 |  | -5330
32 | WARDHA | 5046 |  | 5046 | 12 | HINGOLI | 5336 |  | -5336
16 | LATUR | 4554 |  | 4554 | 3 | AMRAVATI | 6013 |  | -6013
31 | THANE | 4388 |  | 4388 | 13 | JALGAON | 6326 |  | -6326
14 | JALNA | 4265 |  | 4265 | 20 | NASHIK | 6337 |  | -6337
25 | RAIGAD | 4071 |  | 4071 | 8 | CHANDRAPUR | 6386 |  | -6386
12 | HINGOLI | 4052 |  | 4052 | 30 | SOLAPUR | 6768 |  | -6768
33 | WASHIM | 3568 |  | 3568 | 16 | LATUR | 6898 |  | -6898
23 | PARBHANI | 2671 |  | 2671 | 34 | YAVATMAL | 7515 |  | -7515
21 | OSMANABAD | 2482 |  | 2482 | 1 | AHMEDNAGAR | 10318 |  | -10318
26 | RATNAGIRI | 2438 |  | 2438 |  | Grand Total | 150282 |  | -150282
29 | SINDHUDURG | 1785 |  | 1785 | Sr. No. | District | Financial Incomplete Houses as on 17th Dec | Financial Incomplete Houses as on 18th Dec | Achivement From 17th to 18th Dec

## Awaas Plus
AwaasPlus Aadhar Report
|  | Total Registered |  | Total Aadhar Seeded |  | % Seeded |  | Total Aadhar To Be Seeded
#SNo | District Name | Total HH registered | Total members registered | Total Aadhar seeded for HH till date | Total Aadhar seeded for Members till date | % HH | % MM | HH | MM
1 | AHMEDNAGAR | 293600 | 498771 | 283701 | 368282 | 96.6284 | 73.8379 | 9899 | 130489
9 | DHULE | 199567 | 264536 | 182966 | 144014 | 91.6815 | 54.4402 | 16601 | 120522
13 | JALGAON | 316732 | 506297 | 276816 | 299133 | 87.3975 | 59.0825 | 39916 | 207164
14 | JALNA | 221851 | 295766 | 188737 | 194940 | 85.0738 | 65.9102 | 33114 | 100826
19 | NANDURBAR | 199231 | 216185 | 179157 | 157536 | 89.9243 | 72.8709 | 20074 | 58649
20 | NASHIK | 288171 | 477991 | 281126 | 166046 | 97.5553 | 34.7383 | 7045 | 311945
| Total | 1519152 | 2259546 | 1392503 | 1329951 | 91.6632 | 58.8592 | 126649 | 929595
Thread was being aborted.

## PWL & Job card
Job card Mapping Aawas Plus Compare Report As On 17th Dec 2020 | [6 empty] | PWL aadhar seeding Compare Report As On 17th Dec
S.No | District Name | Total HH in Awaas+ | Total HH registered | Job Card Mapped As On 16th Dec | Job Card Mapped As On 17th Dec | Achievement | S.No | District Name | Total Beneficiaries | PWL Aadhar SEEDING As On 16th Dec | PWL Aadhar SEEDING As On 16th Dec | Achievement
| Total | 5760056 | 1082397 | 1081454 | 1081477 | 23 | 1 | AHMEDNAGAR | 55246 | 44497 | 44498 | 1
19 | NANDURBAR | 199231 | 99172 | 99149 | 99153 | 4 | 2 | AKOLA | 46939 | 38558 | 38558 | 0
11 | GONDIA | 143614 | 87833 | 87417 | 87443 | 26 | 3 | AMRAVATI | 92731 | 73090 | 73070 | -20
3 | AMRAVATI | 174143 | 80053 | 79979 | 79988 | 9 | 4 | AURANGABAD | 22745 | 20704 | 20728 | 24
20 | NASHIK | 288171 | 69810 | 69790 | 69796 | 6 | 5 | BEED | 19760 | 16987 | 16988 | 1
13 | JALGAON | 316732 | 63526 | 63503 | 63509 | 6 | 6 | BHANDARA | 62999 | 53733 | 53732 | -1
6 | BHANDARA | 123736 | 57460 | 57439 | 57440 | 1 | 7 | BULDHANA | 29863 | 26843 | 26844 | 1
1 | AHMEDNAGAR | 293600 | 49194 | 49182 | 49186 | 4 | 8 | CHANDRAPUR | 31975 | 29192 | 29199 | 7
30 | SOLAPUR | 207486 | 47672 | 47626 | 47626 | 0 | 9 | DHULE | 50700 | 33455 | 33459 | 4
9 | DHULE | 199567 | 45811 | 45797 | 45801 | 4 | 10 | GADCHIROLI | 23260 | 19165 | 19165 | 0
18 | NANDED | 351308 | 45214 | 45186 | 45186 | 0 | 11 | GONDIA | 92848 | 70636 | 70638 | 2
17 | NAGPUR | 91329 | 42319 | 42310 | 42317 | 7 | 12 | HINGOLI | 11280 | 10432 | 10432 | 0
2 | AKOLA | 93150 | 41525 | 41511 | 41511 | 0 | 13 | JALGAON | 72977 | 49174 | 49276 | 102
34 | YAVATMAL | 349478 | 39169 | 39086 | 39087 | 1 | 14 | JALNA | 13384 | 7832 | 7843 | 11
8 | CHANDRAPUR | 157806 | 30271 | 30267 | 30269 | 2 | 15 | KOLHAPUR | 16389 | 13468 | 13435 | -33
7 | BULDHANA | 236559 | 28226 | 28217 | 28217 | 0 | 16 | LATUR | 10968 | 9286 | 9291 | 5
22 | PALGHAR | 112736 | 25846 | 25843 | 25843 | 0 | 17 | NAGPUR | 44891 | 38593 | 38683 | 90
10 | GADCHIROLI | 102629 | 22102 | 22090 | 22090 | 0 | 18 | NANDED | 50470 | 26220 | 26232 | 12
4 | AURANGABAD | 260947 | 22079 | 22056 | 22056 | 0 | 19 | NANDURBAR | 106835 | 91771 | 91770 | -1
27 | SANGLI | 132583 | 19337 | 19228 | 19231 | 3 | 20 | NASHIK | 71791 | 66563 | 66565 | 2
5 | BEED | 258662 | 18812 | 18787 | 18793 | 6 | 21 | OSMANABAD | 6502 | 5642 | 5656 | 14
24 | PUNE | 113054 | 18569 | 18562 | 18566 | 4 | 22 | PALGHAR | 26349 | 16310 | 16364 | 54
32 | WARDHA | 75113 | 16556 | 16556 | 16556 | 0 | 23 | PARBHANI | 7165 | 6613 | 6618 | 5
15 | KOLHAPUR | 181903 | 15831 | 15914 | 15829 | -85 | 24 | PUNE | 21460 | 15533 | 15533 | 0
28 | SATARA | 118101 | 13874 | 13869 | 13869 | 0 | 25 | RAIGAD | 9418 | 7574 | 7596 | 22
14 | JALNA | 221851 | 12355 | 12351 | 12351 | 0 | 26 | RATNAGIRI | 8039 | 6854 | 6854 | 0
12 | HINGOLI | 124003 | 10493 | 10490 | 10490 | 0 | 27 | SANGLI | 21538 | 18003 | 18002 | -1
16 | LATUR | 152079 | 10283 | 10279 | 10279 | 0 | 28 | SATARA | 14089 | 13391 | 13391 | 0
33 | WASHIM | 143381 | 9789 | 9787 | 9787 | 0 | 29 | SINDHUDURG | 4760 | 4418 | 4418 | 0
25 | RAIGAD | 50390 | 8256 | 8240 | 8255 | 15 | 30 | SOLAPUR | 48036 | 41966 | 41966 | 0
26 | RATNAGIRI | 78746 | 6897 | 6896 | 6896 | 0 | 31 | THANE | 7320 | 6487 | 6490 | 3
23 | PARBHANI | 189536 | 6846 | 6843 | 6843 | 0 | 32 | WARDHA | 17513 | 16030 | 16030 | 0
31 | THANE | 57329 | 6614 | 6613 | 6613 | 0 | 33 | WASHIM | 10886 | 9423 | 9423 | 0
21 | OSMANABAD | 124374 | 6039 | 6027 | 6037 | 10 | 34 | YAVATMAL | 40699 | 38386 | 38387 | 1
29 | SINDHUDURG | 36729 | 4564 | 4564 | 4564 | 0 |  | Total | 1171825 | 946829 | 947134 | 305

## Ujjwala
Ujjwala Compare Report
SNo | District Name | Eligible for lpg connection As On 16th Dec | Eligible for lpg connection As On 17th Dec | Achievement | House with lpg connection As On 16th Dec | House with lpg connection As On 17th Dec | Achievement
1 | AHMEDNAGAR | 23902 | 23916 | 14 | 5809 | 5809 | 0
2 | AKOLA | 22068 | 22078 | 10 | 3555 | 3555 | 0
3 | AMRAVATI | 41726 | 41731 | 5 | 5610 | 5610 | 0
4 | AURANGABAD | 11849 | 11851 | 2 | 2090 | 2090 | 0
5 | BEED | 9209 | 9214 | 5 | 1839 | 1839 | 0
6 | BHANDARA | 23270 | 23302 | 32 | 3121 | 3121 | 0
7 | BULDHANA | 15432 | 15434 | 2 | 2716 | 2716 | 0
8 | CHANDRAPUR | 17130 | 17132 | 2 | 1869 | 1869 | 0
9 | DHULE | 32802 | 32812 | 10 | 4087 | 4087 | 0
10 | GADCHIROLI | 12441 | 12445 | 4 | 962 | 962 | 0
11 | GONDIA | 29915 | 29959 | 44 | 4055 | 4055 | 0
12 | HINGOLI | 6120 | 6124 | 4 | 1120 | 1120 | 0
13 | JALGAON | 30339 | 30364 | 25 | 4698 | 4698 | 0
14 | JALNA | 6403 | 6410 | 7 | 1551 | 1551 | 0
15 | KOLHAPUR | 8104 | 8105 | 1 | 2084 | 2084 | 0
16 | LATUR | 6518 | 6520 | 2 | 1332 | 1332 | 0
17 | NAGPUR | 15841 | 15857 | 16 | 1968 | 1968 | 0
18 | NANDED | 19085 | 19088 | 3 | 3820 | 3820 | 0
19 | NANDURBAR | 76367 | 76390 | 23 | 2956 | 2956 | 0
20 | NASHIK | 52115 | 52128 | 13 | 6956 | 6956 | 0
21 | OSMANABAD | 3193 | 3193 | 0 | 783 | 783 | 0
22 | PALGHAR | 22557 | 22572 | 15 | 2061 | 2061 | 0
23 | PARBHANI | 4004 | 4005 | 1 | 931 | 931 | 0
24 | PUNE | 9574 | 9580 | 6 | 1522 | 1522 | 0
25 | RAIGAD | 5998 | 6000 | 2 | 396 | 396 | 0
26 | RATNAGIRI | 3985 | 3986 | 1 | 879 | 879 | 0
27 | SANGLI | 8997 | 9010 | 13 | 1929 | 1929 | 0
28 | SATARA | 6717 | 6722 | 5 | 1938 | 1938 | 0
29 | SINDHUDURG | 2576 | 2576 | 0 | 433 | 433 | 0
30 | SOLAPUR | 19784 | 19785 | 1 | 4935 | 4935 | 0
31 | THANE | 5805 | 5805 | 0 | 249 | 249 | 0
32 | WARDHA | 8271 | 8275 | 4 | 1732 | 1732 | 0
33 | WASHIM | 5498 | 5498 | 0 | 1086 | 1086 | 0
34 | YAVATMAL | 21632 | 21636 | 4 | 3767 | 3767 | 0
| Total | 589227 | 589503 | 276 | 84839 | 84839 | 0

## Mgnrega
MGNREGA Compare Report As On 17th Dec
Sr.No | District | Total Mandays As On 16th Dec | Total Mandays As On 17th Dec | Achivement
1 | AHMEDNAGAR | 33769 | 33795 | 26
2 | AKOLA | 28203 | 28210 | 7
3 | AMRAVATI | 52559 | 52578 | 19
4 | AURANGABAD | 20014 | 20021 | 7
5 | BEED | 13025 | 13025 | 0
6 | BHANDARA | 36173 | 36238 | 65
7 | BULDHANA | 27252 | 27253 | 1
8 | CHANDRAPUR | 31015 | 31036 | 21
9 | DHULE | 40252 | 40274 | 22
10 | GADCHIROLI | 20881 | 20890 | 9
11 | GONDIA | 39622 | 39687 | 65
12 | HINGOLI | 6910 | 6910 | 0
13 | JALGAON | 38084 | 38099 | 15
14 | JALNA | 4276 | 4280 | 4
15 | KOLHAPUR | 11511 | 11511 | 0
16 | LATUR | 16843 | 16849 | 6
17 | NAGPUR | 20501 | 20514 | 13
18 | NANDED | 21452 | 21453 | 1
19 | NANDURBAR | 84948 | 84958 | 10
20 | NASHIK | 67544 | 67556 | 12
21 | OSMANABAD | 8593 | 8593 | 0
22 | PALGHAR | 22252 | 22258 | 6
23 | PARBHANI | 8856 | 8858 | 2
24 | PUNE | 14001 | 14004 | 3
25 | RAIGAD | 1715 | 1715 | 0
26 | RATNAGIRI | 6796 | 6801 | 5
27 | SANGLI | 10493 | 10494 | 1
28 | SATARA | 12577 | 12579 | 2
29 | SINDHUDURG | 1341 | 1342 | 1
30 | SOLAPUR | 14713 | 14713 | 0
31 | THANE | 7467 | 7467 | 0
32 | WARDHA | 14633 | 14645 | 12
33 | WASHIM | 13755 | 13763 | 8
34 | YAVATMAL | 36251 | 36271 | 20
| Total | 788277 | 788640 | 363

## Compared report
Cummulative PMAY-G Online Progress Report From 15th Nov To 14th Dec 2020 | [8 empty] | State scheme
SNo | District Name | Target PMAYG | Sanction |  | 1st installment |  | Complation |  | State scheme | Sanction |  | 1st installment |  | Complation |  | Total Progress
|  |  | Progress on 14/12/2020 | Remaining | Progress on 14/12/2020 | Remaining | Progress on 14/12/2020 | Remaining | Target States Scheme | Progress on 14/12/2020 | Remaining Sanction | Progress on 14/12/2020 | Yet to give 1st Inst | Progress on 14/12/2020 | Incomplet
1 | BEED | 20320 | -3 | 6382 | 0 | 2775 | 8 | 11424 | 13236 | 2 | 4206 | 0 | 347 | 1 | 6605 | 842
2 | BHANDARA | 63597 | 0 | 27124 | 0 | 8039 | 53 | 43584 | 15386 | 0 | 1071 | 0 | 1738 | 3 | 8231 | 585
3 | NAGPUR | 45792 | 188 | 14970 | 0 | 11315 | 19 | 31206 | 9482 | 0 | 350 | 0 | 1110 | 2 | 2964 | 578
4 | JALGAON | 75723 | 0 | 28442 | 0 | 10151 | 5 | 46662 | 17383 | 38 | 1288 | 0 | 3831 | 0 | 8409 | 404
5 | GONDIA | 92862 | 1128 | 23431 | 0 | 28467 | 19 | 68038 | 13480 | 0 | 4121 | 0 | 1430 | 3 | 8512 | 182
6 | KOLHAPUR | 17047 | 0 | 4394 | 0 | 2933 | 33 | 9162 | 10935 | 0 | 99 | 0 | 1945 | 7 | 3134 | 171
7 | PUNE | 21818 | 0 | 9083 | 0 | 1226 | 1 | 12979 | 10457 | 7 | 1730 | 0 | 658 | 1 | 4115 | 168
8 | NASHIK | 72630 | 13 | 5447 | 0 | 7592 | 92 | 24447 | 19111 | 0 | 1209 | 0 | 3382 | 15 | 9992 | 143
9 | SATARA | 14166 | 3 | 3146 | 0 | 3543 | 12 | 7901 | 9559 | 0 | 54 | 0 | 1796 | 0 | 2859 | 128
10 | NANDURBAR | 111956 | 0 | 13694 | 0 | 8909 | 17 | 49734 | 10307 | 0 | 476 | 0 | 640 | 0 | 4201 | 105
11 | PALGHAR | 26966 | -15 | 1298 | 0 | 919 | 50 | 6237 | 6455 | 0 | 649 | 0 | 316 | 8 | 2545 | 93
12 | RAIGAD | 9566 | 0 | 2286 | 0 | 669 | 6 | 3702 | 3833 | 0 | 30 | 0 | 414 | 9 | 867 | 84
13 | DHULE | 52614 | 98 | 8292 | 0 | 7062 | 56 | 22695 | 12351 | 0 | 434 | 0 | 1282 | 22 | 4587 | 78
14 | NANDED | 50791 | 0 | 10791 | 0 | 13767 | 52 | 32890 | 17863 | 0 | 7807 | 0 | 946 | 21 | 11986 | 73
15 | SOLAPUR | 49500 | 18 | 17311 | 0 | 9655 | 14 | 30925 | 15433 | 0 | 389 | 0 | 2260 | 0 | 4382 | 71
16 | AMRAVATI | 93272 | 0 | 39183 | 0 | 5966 | 25 | 55196 | 14486 | 0 | 594 | 0 | 3176 | 9 | 6380 | 63
17 | CHANDRAPUR | 32694 | 257 | 5257 | 0 | 7767 | 11 | 16918 | 24728 | 0 | 8154 | 0 | 1312 | 15 | 16839 | 49
18 | AHMEDNAGAR | 56134 | 0 | 20508 | 0 | 5901 | 26 | 35023 | 30450 | 15 | 2409 | 0 | 4498 | 3 | 14728 | 44
19 | OSMANABAD | 6632 | 0 | 1723 | 0 | 1132 | 0 | 3487 | 15251 | 9 | 6864 | 0 | 2388 | 0 | 10844 | 35
20 | YAVATMAL | 41521 | 30 | 9755 | 0 | 6624 | 6 | 21707 | 19265 | 0 | 319 | 0 | 2472 | 22 | 9670 | 28
21 | AKOLA | 47181 | 0 | 15626 | 0 | 5215 | 15 | 27405 | 14198 | 0 | 801 | 0 | 4184 | 7 | 8310 | 22
22 | BULDHANA | 30604 | 10 | 10896 | 0 | 2043 | 14 | 16295 | 12190 | 0 | 195 | 0 | 2792 | 2 | 4512 | 16
23 | AURANGABAD | 23273 | 0 | 1643 | 0 | 7601 | 4 | 12334 | 17770 | 0 | 1324 | 0 | 7939 | 10 | 11683 | 14
24 | WARDHA | 17575 | 147 | 7255 | 0 | 984 | 4 | 9935 | 8310 | 0 | 13 | 0 | 542 | 4 | 3635 | 8
25 | RATNAGIRI | 8100 | 18 | 2016 | 0 | 1889 | 3 | 4252 | 5864 | 4 | 8 | 0 | 358 | 0 | 1318 | 7
26 | WASHIM | 11091 | 0 | 4579 | 0 | 116 | 3 | 5864 | 7712 | 0 | 14 | 0 | 2180 | 2 | 3864 | 5
27 | HINGOLI | 11335 | 479 | 3352 | 0 | 791 | 3 | 5368 | 9745 | 0 | 1380 | 0 | 635 | 1 | 3575 | 4
28 | JALNA | 13465 | 2 | 5274 | 0 | 655 | 0 | 7488 | 7135 | 0 | 2012 | 0 | 178 | 3 | 3928 | 3
29 | PARBHANI | 7603 | 0 | 1194 | 0 | 1649 | 0 | 3688 | 14543 | 0 | 2253 | 0 | 1372 | 2 | 5466 | 2
30 | GADCHIROLI | 23746 | 29 | 3326 | 0 | 4404 | 4 | 12669 | 11477 | 0 | 1372 | 0 | 1377 | 6 | 6181 | 1
31 | SANGLI | 22172 | 0 | 10023 | 0 | 877 | 0 | 13423 | 7082 | 0 | 853 | 0 | 918 | 1 | 2479 | 1
32 | SINDHUDURG | 4947 | 270 | 1804 | 0 | 251 | 0 | 2427 | 1851 | 0 | 17 | 0 | 308 | 1 | 402 | 1
33 | THANE | 7395 | 0 | 912 | 0 | 263 | 0 | 1909 | 3524 | 0 | 260 | 0 | 27 | 1 | 834 | 1
34 | LATUR | 11302 | 0 | 3807 | 0 | 260 | 0 | 4936 | 19992 | 0 | 3988 | 0 | 2615 | 0 | 9536 | 0
| Total | 1195390 | 2672 | 383066 | 5454 | 117737 | 5544 | 664859 | 430844 | 75 | 56743 | 0 | 61366 | 181 | 207573