## Landless
S. N. | District | AS On 20th Nov | [5 empty] | As On 7th Dec |  |  |  |  | Achivement
|  | Landless beneficiaries in PWL | Landless Beneficiaries Provided Land |  |  |  |  | Landless Beneficiaries provided Land
|  |  | PDU | Free Govt. land | Encroachment Regularization | Other | Total | PDU | Free Govt. Land | Encroachment Regularisation | Other | Total
1 | AMRAVATI | 14998 | 223 | 0 | 0 | 0 | 223 | 267 | 3295 | 3396 | 0 | 6958 | 6735
2 | BULDHANA | 4942 | 0 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 257 | 257
3 | WASHIM | 574 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 470 | 0 | 494 | 494
4 | AKOLA | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | YAVATMAL | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NAGPUR | 10344 | 26 | 0 | 0 | 0 | 26 | 49 | 343 | 0 | 0 | 392 | 366
7 | BHANDARA | 4626 | 0 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 257 | 257
8 | CHANDRAPUR | 1300 | 16 | 0 | 0 | 0 | 16 | 44 | 0 | 114 | 0 | 158 | 142
9 | WARDHA | 1129 | 75 | 0 | 0 | 0 | 75 | 91 | 42 | 0 | 0 | 133 | 58
10 | GONDIA | 262 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
11 | GADCHIROLI | 17 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0
12 | AHMEDNAGAR | 9281 | 203 | 0 | 0 | 0 | 203 | 68 | 158 | 0 | 0 | 226 | 23
13 | JALGAON | 9718 | 4932 | 0 | 0 | 0 | 4932 | 776 | 1122 | 0 | 5813 | 7711 | 2779
14 | NASHIK | 611 | 81 | 0 | 0 | 0 | 81 | 81 | 0 | 0 | 0 | 81 | 0
15 | NANDURBAR | 98 | 0 | 0 | 0 | 0 | 0 | 49 | 343 | 0 | 0 | 392 | 392
16 | DHULE | 37 | 37 | 0 | 0 | 0 | 37 | 41 | 0 | 0 | 0 | 41 | 4
17 | SOLAPUR | 5903 | 54 | 0 | 0 | 0 | 54 | 77 | 484 | 0 | 0 | 561 | 507
18 | KOLHAPUR | 1470 | 17 | 0 | 0 | 0 | 17 | 35 | 0 | 0 | 0 | 35 | 18
19 | SATARA | 1562 | 9 | 6 | 10 | 0 | 25 | 9 | 6 | 10 | 0 | 25 | 0
20 | PUNE | 1103 | 33 | 0 | 0 | 0 | 33 | 46 | 923 | 0 | 0 | 969 | 936
21 | SANGLI | 567 | 51 | 0 | 0 | 0 | 51 | 38 | 60 | 0 | 0 | 98 | 47
22 | JALNA | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | AURANGABAD | 615 | 137 | 0 | 0 | 0 | 137 | 68 | 158 | 0 | 0 | 226 | 89
24 | LATUR | 410 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 5 | 0
25 | HINGOLI | 394 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 125 | 125
26 | OSMANABAD | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | NANDED | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | BEED | 110 | 88 | 0 | 0 | 0 | 88 | 88 | 0 | 0 | 0 | 88 | 0
29 | PARBHANI | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | RAIGAD | 445 | 17 | 0 | 0 | 0 | 17 | 17 | 0 | 0 | 0 | 17 | 0
31 | SINDHUDURG | 392 | 11 | 0 | 0 | 0 | 11 | 57 | 0 | 0 | 0 | 57 | 46
32 | RATNAGIRI | 219 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 0
33 | THANE | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19
34 | PALGHAR | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 73052 | 9168 | 0 | 0 | 0 | 9168 | 2573 | 6934 | 3990 | 5832 | 19329 | 13295

## PMAY-G
Cummulative PMAY-G Online Progress Report From 18th Dec 2020
SNo | District Name | Target | Sanctions Out of GEO Tagged |  |  |  | 1st Installment |  |  |  | Completion
|  |  | As On 17th Nov | As On 18th Dec | Achievement | Remaining | As On 17th Dec | As On 18th Dec | Achievement | Remaining | As On 17th Dec | As On 18th Dec | Achievement | Remaining
1 | AHMEDNAGAR | 56134 | 35623 | 35623 | 0 | 20511 | 29761 | 29761 | 0 | 5862 | 21176 | 21195 | 19 | 34939
2 | AKOLA | 47181 | 31555 | 31918 | 363 | 15263 | 26560 | 26560 | 0 | 5358 | 19815 | 19823 | 8 | 27358
3 | AMRAVATI | 93272 | 54670 | 55227 | 557 | 38045 | 48391 | 48391 | 0 | 6836 | 38121 | 38137 | 16 | 55135
4 | AURANGABAD | 23273 | 21630 | 21630 | 0 | 1643 | 14333 | 14333 | 0 | 7297 | 10943 | 10946 | 3 | 12327
5 | BEED | 20320 | 15630 | 15630 | 0 | 4690 | 11172 | 11172 | 0 | 4458 | 8900 | 8900 | 0 | 11420
6 | BHANDARA | 63597 | 36473 | 36473 | 0 | 27124 | 28675 | 28675 | 0 | 7798 | 20080 | 20107 | 27 | 43490
7 | BULDHANA | 30604 | 19708 | 19708 | 0 | 10896 | 17708 | 17708 | 0 | 2000 | 14319 | 14348 | 29 | 16256
8 | CHANDRAPUR | 32694 | 27463 | 27464 | 1 | 5230 | 21162 | 21162 | 0 | 6302 | 15787 | 15790 | 3 | 16904
9 | DHULE | 52614 | 44325 | 44327 | 2 | 8287 | 37636 | 37636 | 0 | 6691 | 29954 | 29990 | 36 | 22624
10 | GADCHIROLI | 23746 | 20419 | 20419 | 0 | 3327 | 16076 | 16076 | 0 | 4343 | 11089 | 11096 | 7 | 12650
11 | GONDIA | 92862 | 69752 | 70527 | 775 | 22335 | 42251 | 42251 | 0 | 28276 | 24883 | 24905 | 22 | 67957
12 | HINGOLI | 11335 | 7983 | 7983 | 0 | 3352 | 7244 | 7244 | 0 | 739 | 5978 | 5980 | 2 | 5355
13 | JALGAON | 75723 | 47383 | 47399 | 16 | 28324 | 38027 | 38027 | 0 | 9372 | 29091 | 29098 | 7 | 46625
14 | JALNA | 13465 | 8191 | 8191 | 0 | 5274 | 7557 | 7557 | 0 | 634 | 5983 | 5987 | 4 | 7478
15 | KOLHAPUR | 17047 | 12697 | 12724 | 27 | 4323 | 9730 | 9730 | 0 | 2994 | 7886 | 7886 | 0 | 9161
16 | LATUR | 11302 | 7495 | 7495 | 0 | 3807 | 7236 | 7236 | 0 | 259 | 6368 | 6368 | 0 | 4934
17 | NAGPUR | 45792 | 31515 | 31574 | 59 | 14218 | 19618 | 19618 | 0 | 11956 | 14604 | 14608 | 4 | 31184
18 | NANDED | 50791 | 40000 | 40000 | 0 | 10791 | 26375 | 26375 | 0 | 13625 | 17967 | 18011 | 44 | 32780
19 | NANDURBAR | 111956 | 98261 | 98391 | 130 | 13565 | 91220 | 91220 | 0 | 7171 | 62342 | 62401 | 59 | 49555
20 | NASHIK | 72630 | 67224 | 67238 | 14 | 5392 | 61029 | 61029 | 0 | 6209 | 48284 | 48315 | 31 | 24315
21 | OSMANABAD | 6632 | 4910 | 4947 | 37 | 1685 | 3882 | 3882 | 0 | 1065 | 3145 | 3145 | 0 | 3487
22 | PALGHAR | 26966 | 25687 | 25687 | 0 | 1279 | 24855 | 24855 | 0 | 832 | 20796 | 20807 | 11 | 6159
23 | PARBHANI | 7603 | 6409 | 6409 | 0 | 1194 | 4775 | 4775 | 0 | 1634 | 3916 | 3916 | 0 | 3687
24 | PUNE | 21818 | 12960 | 12960 | 0 | 8858 | 11523 | 11523 | 0 | 1437 | 8844 | 8845 | 1 | 12973
25 | RAIGAD | 9566 | 7295 | 7295 | 0 | 2271 | 6682 | 6682 | 0 | 613 | 5874 | 5874 | 0 | 3692
26 | RATNAGIRI | 8100 | 6084 | 6084 | 0 | 2016 | 4210 | 4210 | 0 | 1874 | 3852 | 3854 | 2 | 4246
27 | SANGLI | 22172 | 12879 | 12997 | 118 | 9175 | 11341 | 11341 | 0 | 1656 | 8775 | 8775 | 0 | 13397
28 | SATARA | 14166 | 11046 | 11031 | -15 | 3135 | 7493 | 7493 | 0 | 3538 | 6275 | 6279 | 4 | 7887
29 | SINDHUDURG | 4947 | 3143 | 3143 | 0 | 1804 | 2901 | 2901 | 0 | 242 | 2520 | 2522 | 2 | 2425
30 | SOLAPUR | 49500 | 32656 | 32827 | 171 | 16673 | 22538 | 22538 | 0 | 10289 | 18607 | 18608 | 1 | 30892
31 | THANE | 7395 | 6492 | 6493 | 1 | 902 | 6221 | 6221 | 0 | 272 | 5494 | 5494 | 0 | 1901
32 | WARDHA | 17575 | 10816 | 11005 | 189 | 6570 | 9357 | 9357 | 0 | 1648 | 7648 | 7652 | 4 | 9923
33 | WASHIM | 11091 | 6512 | 6512 | 0 | 4579 | 6396 | 6396 | 0 | 116 | 5229 | 5229 | 0 | 5862
34 | YAVATMAL | 41521 | 31766 | 31766 | 0 | 9755 | 25179 | 25179 | 0 | 6587 | 19835 | 19844 | 9 | 21677
| Total | 1195390 | 876652 | 879097 | 2445 | 316293 | 709114 | 709114 | 0 | 169983 | 534380 | 534735 | 355 | 660655

## State Scheme
Yesterday 17.12.2020 | [8 empty] | Today 18.12.2020
. |  |  |  |  | Installment |  |  |  | . |  |  |  |  | Installment |  |  |  | State Scheme Report Cumulative
[21 empty] | Sanctions Out of GEO Tagged |  |  |  | 1st Installment |  |  |  | Completion
#SNo | District Name | Target fixed by States | Sanctions Out of GEO Tagged | Remaining Sanction | 1st | Remaining 1st Installment | Completed | Incompleted | #SNo | District Name | Target fixed by States | Sanctions Out of GEO Tagged | Remaining Sanction | 1st | Remaining 1st Installment | Completed | Incompleted | #SNo | District Name | Target fixed by States | 17.12.2020 | 18.12.2020 | Achievement | Remaining Sanction | 17.12.2020 | 18.12.2020 | Achievement | Yet to give 1st Inst | 17.12.2020 | 18.12.2020 | Achievement | Incompleted
1 | AHMEDNAGAR | 30450 | 28085 | 2365 | 23691 | 4394 | 15756 | 14694 | 1 | AHMEDNAGAR | 30450 | 28085 | 2365 | 23691 | 4394 | 15803 | 14647 | 1 | AHMEDNAGAR | 30450 | 28085 | 28085 | 0 | 2365 | 23691 | 23691 | 0 | 4394 | 15756 | 15803 | 47 | 14647
2 | AKOLA | 14198 | 13397 | 801 | 9221 | 4176 | 5908 | 8290 | 2 | AKOLA | 14198 | 13397 | 801 | 9225 | 4172 | 5911 | 8287 | 2 | AKOLA | 14198 | 13397 | 13397 | 0 | 801 | 9221 | 9213 | 8 | 4184 | 5908 | 5911 | 3 | 8287
3 | AMRAVATI | 14486 | 13893 | 593 | 10719 | 3174 | 8121 | 6365 | 3 | AMRAVATI | 14486 | 13890 | 596 | 10748 | 3142 | 8126 | 6360 | 3 | AMRAVATI | 14486 | 13893 | 13890 | -3 | 596 | 10719 | 10716 | 3 | 3174 | 8121 | 8126 | 5 | 6360
4 | AURANGABAD | 17770 | 16446 | 1324 | 8518 | 7928 | 6100 | 11670 | 4 | AURANGABAD | 17770 | 16446 | 1324 | 8518 | 7928 | 6108 | 11662 | 4 | AURANGABAD | 17770 | 16446 | 16446 | 0 | 1324 | 8518 | 8507 | 11 | 7939 | 6100 | 6108 | 8 | 11662
5 | BEED | 13236 | 9031 | 4205 | 8683 | 348 | 6631 | 6605 | 5 | BEED | 13236 | 9031 | 4205 | 8695 | 336 | 6631 | 6605 | 5 | BEED | 13236 | 9031 | 9031 | 0 | 4205 | 8683 | 8683 | 0 | 348 | 6631 | 6631 | 0 | 6605
6 | BHANDARA | 15386 | 14315 | 1071 | 12599 | 1716 | 7163 | 8223 | 6 | BHANDARA | 15386 | 14315 | 1071 | 12612 | 1703 | 7164 | 8222 | 6 | BHANDARA | 15386 | 14315 | 14315 | 0 | 1071 | 12599 | 12577 | 22 | 1738 | 7163 | 7164 | 1 | 8222
7 | BULDHANA | 12190 | 11995 | 195 | 9206 | 2789 | 7686 | 4504 | 7 | BULDHANA | 12190 | 11995 | 195 | 9207 | 2788 | 7690 | 4500 | 7 | BULDHANA | 12190 | 11995 | 11995 | 0 | 195 | 9206 | 9203 | 3 | 2792 | 7686 | 7690 | 4 | 4500
8 | CHANDRAPUR | 24728 | 16603 | 8125 | 15303 | 1300 | 7924 | 16804 | 8 | CHANDRAPUR | 24728 | 16604 | 8124 | 15315 | 1289 | 7931 | 16797 | 8 | CHANDRAPUR | 24728 | 16603 | 16604 | 1 | 8124 | 15303 | 15262 | 41 | 1342 | 7924 | 7931 | 7 | 16797
9 | DHULE | 12351 | 11917 | 434 | 10635 | 1282 | 7794 | 4557 | 9 | DHULE | 12351 | 11917 | 434 | 10635 | 1282 | 7828 | 4523 | 9 | DHULE | 12351 | 11917 | 11917 | 0 | 434 | 10635 | 10635 | 0 | 1282 | 7794 | 7828 | 34 | 4523
10 | GADCHIROLI | 11477 | 10105 | 1372 | 8728 | 1377 | 5314 | 6163 | 10 | GADCHIROLI | 11477 | 10105 | 1372 | 8728 | 1377 | 5323 | 6154 | 10 | GADCHIROLI | 11477 | 10105 | 10105 | 0 | 1372 | 8728 | 8728 | 0 | 1377 | 5314 | 5323 | 9 | 6154
11 | GONDIA | 13480 | 9364 | 4116 | 7939 | 1425 | 4989 | 8491 | 11 | GONDIA | 13480 | 9359 | 4121 | 8003 | 1356 | 4998 | 8482 | 11 | GONDIA | 13480 | 9364 | 9359 | -5 | 4121 | 7939 | 7929 | 10 | 1430 | 4989 | 4998 | 9 | 8482
12 | HINGOLI | 9745 | 8365 | 1380 | 7730 | 635 | 6184 | 3561 | 12 | HINGOLI | 9745 | 8365 | 1380 | 7730 | 635 | 6189 | 3556 | 12 | HINGOLI | 9745 | 8365 | 8365 | 0 | 1380 | 7730 | 7730 | 0 | 635 | 6184 | 6189 | 5 | 3556
13 | JALGAON | 17383 | 16095 | 1288 | 12308 | 3787 | 8990 | 8393 | 13 | JALGAON | 17383 | 16095 | 1288 | 12349 | 3746 | 9001 | 8382 | 13 | JALGAON | 17383 | 16095 | 16095 | 0 | 1288 | 12308 | 12264 | 44 | 3831 | 8990 | 9001 | 11 | 8382
14 | JALNA | 7135 | 5123 | 2012 | 4950 | 173 | 3210 | 3925 | 14 | JALNA | 7135 | 5123 | 2012 | 4950 | 173 | 3232 | 3903 | 14 | JALNA | 7135 | 5123 | 5123 | 0 | 2012 | 4950 | 4945 | 5 | 178 | 3210 | 3232 | 22 | 3903
15 | KOLHAPUR | 10935 | 10836 | 99 | 8891 | 1945 | 7814 | 3121 | 15 | KOLHAPUR | 10935 | 10836 | 99 | 8891 | 1945 | 7814 | 3121 | 15 | KOLHAPUR | 10935 | 10836 | 10836 | 0 | 99 | 8891 | 8891 | 0 | 1945 | 7814 | 7814 | 0 | 3121
16 | LATUR | 19992 | 16004 | 3988 | 13389 | 2615 | 10458 | 9534 | 16 | LATUR | 19992 | 16004 | 3988 | 13389 | 2615 | 10460 | 9532 | 16 | LATUR | 19992 | 16004 | 16004 | 0 | 3988 | 13389 | 13389 | 0 | 2615 | 10458 | 10460 | 2 | 9532
17 | NAGPUR | 9482 | 9132 | 350 | 8032 | 1100 | 6525 | 2957 | 17 | NAGPUR | 9482 | 9132 | 350 | 8044 | 1088 | 6527 | 2955 | 17 | NAGPUR | 9482 | 9132 | 9132 | 0 | 350 | 8032 | 8022 | 10 | 1110 | 6525 | 6527 | 2 | 2955
18 | NANDED | 17863 | 10056 | 7807 | 9110 | 946 | 5889 | 11974 | 18 | NANDED | 17863 | 10056 | 7807 | 9118 | 938 | 5910 | 11953 | 18 | NANDED | 17863 | 10056 | 10056 | 0 | 7807 | 9110 | 9110 | 0 | 946 | 5889 | 5910 | 21 | 11953
19 | NANDURBAR | 10307 | 9835 | 472 | 9191 | 644 | 6106 | 4201 | 19 | NANDURBAR | 10307 | 9835 | 472 | 9193 | 642 | 6112 | 4195 | 19 | NANDURBAR | 10307 | 9835 | 9835 | 0 | 472 | 9191 | 9191 | 0 | 644 | 6106 | 6112 | 6 | 4195
20 | NASHIK | 19111 | 17941 | 1170 | 14523 | 3418 | 9142 | 9969 | 20 | NASHIK | 19111 | 17941 | 1170 | 14534 | 3407 | 9158 | 9953 | 20 | NASHIK | 19111 | 17941 | 17941 | 0 | 1170 | 14523 | 14520 | 3 | 3421 | 9142 | 9158 | 16 | 9953
21 | OSMANABAD | 15251 | 8387 | 6864 | 6003 | 2384 | 4409 | 10842 | 21 | OSMANABAD | 15251 | 8387 | 6864 | 6003 | 2384 | 4410 | 10841 | 21 | OSMANABAD | 15251 | 8387 | 8387 | 0 | 6864 | 6003 | 5999 | 4 | 2388 | 4409 | 4410 | 1 | 10841
22 | PALGHAR | 6455 | 5806 | 649 | 5495 | 311 | 3921 | 2534 | 22 | PALGHAR | 6455 | 5806 | 649 | 5557 | 249 | 3925 | 2530 | 22 | PALGHAR | 6455 | 5806 | 5806 | 0 | 649 | 5495 | 5490 | 5 | 316 | 3921 | 3925 | 4 | 2530
23 | PARBHANI | 14543 | 12290 | 2253 | 10920 | 1370 | 9093 | 5450 | 23 | PARBHANI | 14543 | 12290 | 2253 | 10920 | 1370 | 9093 | 5450 | 23 | PARBHANI | 14543 | 12290 | 12290 | 0 | 2253 | 10920 | 10918 | 2 | 1372 | 9093 | 9093 | 0 | 5450
24 | PUNE | 10457 | 8727 | 1730 | 8132 | 595 | 6351 | 4106 | 24 | PUNE | 10457 | 8805 | 1652 | 8146 | 659 | 6352 | 4105 | 24 | PUNE | 10457 | 8727 | 8805 | 78 | 1652 | 8132 | 8069 | 63 | 736 | 6351 | 6352 | 1 | 4105
25 | RAIGAD | 3833 | 3803 | 30 | 3393 | 410 | 2973 | 860 | 25 | RAIGAD | 3833 | 3803 | 30 | 3393 | 410 | 2977 | 856 | 25 | RAIGAD | 3833 | 3803 | 3803 | 0 | 30 | 3393 | 3389 | 4 | 414 | 2973 | 2977 | 4 | 856
26 | RATNAGIRI | 5864 | 5858 | 6 | 5498 | 360 | 4568 | 1296 | 26 | RATNAGIRI | 5864 | 5858 | 6 | 5503 | 355 | 4568 | 1296 | 26 | RATNAGIRI | 5864 | 5858 | 5858 | 0 | 6 | 5498 | 5498 | 0 | 360 | 4568 | 4568 | 0 | 1296
27 | SANGLI | 7082 | 6234 | 848 | 5311 | 923 | 4604 | 2478 | 27 | SANGLI | 7082 | 6243 | 839 | 5311 | 932 | 4604 | 2478 | 27 | SANGLI | 7082 | 6234 | 6243 | 9 | 839 | 5311 | 5311 | 0 | 932 | 4604 | 4604 | 0 | 2478
28 | SATARA | 9559 | 9505 | 54 | 7709 | 1796 | 6733 | 2826 | 28 | SATARA | 9559 | 9505 | 54 | 7712 | 1793 | 6736 | 2823 | 28 | SATARA | 9559 | 9505 | 9505 | 0 | 54 | 7709 | 7709 | 0 | 1796 | 6733 | 6736 | 3 | 2823
29 | SINDHUDURG | 1851 | 1834 | 17 | 1526 | 308 | 1450 | 401 | 29 | SINDHUDURG | 1851 | 1834 | 17 | 1526 | 308 | 1450 | 401 | 29 | SINDHUDURG | 1851 | 1834 | 1834 | 0 | 17 | 1526 | 1526 | 0 | 308 | 1450 | 1450 | 0 | 401
30 | SOLAPUR | 15433 | 15044 | 389 | 12784 | 2260 | 11055 | 4378 | 30 | SOLAPUR | 15433 | 15044 | 389 | 12786 | 2258 | 11059 | 4374 | 30 | SOLAPUR | 15433 | 15044 | 15044 | 0 | 389 | 12784 | 12784 | 0 | 2260 | 11055 | 11059 | 4 | 4374
31 | THANE | 3524 | 3264 | 260 | 3237 | 27 | 2701 | 823 | 31 | THANE | 3524 | 3264 | 260 | 3244 | 20 | 2702 | 822 | 31 | THANE | 3524 | 3264 | 3264 | 0 | 260 | 3237 | 3237 | 0 | 27 | 2701 | 2702 | 1 | 822
32 | WARDHA | 8310 | 8297 | 13 | 7757 | 540 | 4701 | 3609 | 32 | WARDHA | 8310 | 8297 | 13 | 7758 | 539 | 4708 | 3602 | 32 | WARDHA | 8310 | 8297 | 8297 | 0 | 13 | 7757 | 7755 | 2 | 542 | 4701 | 4708 | 7 | 3602
33 | WASHIM | 7712 | 7698 | 14 | 5521 | 2177 | 3849 | 3863 | 33 | WASHIM | 7712 | 7698 | 14 | 5522 | 2176 | 3849 | 3863 | 33 | WASHIM | 7712 | 7698 | 7698 | 0 | 14 | 5521 | 5518 | 3 | 2180 | 3849 | 3849 | 0 | 3863
34 | YAVATMAL | 19265 | 18946 | 319 | 16474 | 2472 | 9636 | 9629 | 34 | YAVATMAL | 19265 | 18946 | 319 | 16474 | 2472 | 9645 | 9620 | 34 | YAVATMAL | 19265 | 18946 | 18946 | 0 | 319 | 16474 | 16474 | 0 | 2472 | 9636 | 9645 | 9 | 9620
| Total | 430844 | 374231 | 56613 | 313126 | 61105 | 223748 | 207096 |  | Total | 430844 | 374311 | 56533 | 313430 | 60881 | 223994 | 206850 |  | Total | 430844 | 374231 | 374311 | 80 | 56533 | 313126 | 312883 | 243 | 61428 | 223748 | 223994 | 246 | 206850

## Delayed Houses
SNo | District Name | Houses not completed even after 12 Months after receiving First Installment(17/12/2020) | Houses not completed even after 12 Months after receiving First Installment(18/12/2020) | Achievement
1 | AHMEDNAGAR | 6167 | 6151 | -16
2 | AKOLA | 4554 | 4547 | -7
3 | AMRAVATI | 6556 | 6546 | -10
4 | AURANGABAD | 2023 | 2023 | 0
5 | BEED | 1258 | 1258 | 0
6 | BHANDARA | 2691 | 2677 | -14
7 | BULDHANA | 2224 | 2200 | -24
8 | CHANDRAPUR | 2564 | 2562 | -2
9 | DHULE | 4916 | 4893 | -23
10 | GADCHIROLI | 3182 | 3176 | -6
11 | GONDIA | 2911 | 2906 | -5
12 | HINGOLI | 433 | 433 | 0
13 | JALGAON | 5344 | 5340 | -4
14 | JALNA | 853 | 851 | -2
15 | KOLHAPUR | 1068 | 1068 | 0
16 | LATUR | 669 | 669 | 0
17 | NAGPUR | 1568 | 1568 | 0
18 | NANDED | 5538 | 5516 | -22
19 | NANDURBAR | 15072 | 15033 | -39
20 | NASHIK | 5794 | 5772 | -22
21 | OSMANABAD | 438 | 438 | 0
22 | PALGHAR | 1514 | 1507 | -7
23 | PARBHANI | 578 | 578 | 0
24 | PUNE | 1658 | 1657 | -1
25 | RAIGAD | 479 | 479 | 0
26 | RATNAGIRI | 184 | 182 | -2
27 | SANGLI | 1715 | 1715 | 0
28 | SATARA | 835 | 831 | -4
29 | SINDHUDURG | 125 | 123 | -2
30 | SOLAPUR | 3267 | 3266 | -1
31 | THANE | 527 | 527 | 0
32 | WARDHA | 1164 | 1161 | -3
33 | WASHIM | 933 | 933 | 0
34 | YAVATMAL | 3965 | 3957 | -8
| Total | 92767 | 92543 | -224

## Financial Completion
PMAY-G District Financial Incomplete Houses |  |  |  |  | State Schemes District Financial Incomplete Houses
Sr. No. | District | Financial Incomplete Houses as on 17th Dec | Financial Incomplete Houses as on 18th Dec | Achivement From 17th to 18th Dec | Sr. No. | District | Financial Incomplete Houses as on 17th Dec | Financial Incomplete Houses as on 18th Dec | Achivement From 17th to 18th Dec
1 | AHMEDNAGAR | 13886 | 13905 | -19 | 1 | AHMEDNAGAR | 10318 | 10365 | 47
2 | AKOLA | 11569 | 11577 | -8 | 2 | AKOLA | 3905 | 3902 | -3
3 | AMRAVATI | 22833 | 22849 | -16 | 3 | AMRAVATI | 6013 | 6017 | 4
4 | AURANGABAD | 6663 | 6666 | -3 | 4 | AURANGABAD | 4222 | 4230 | 8
5 | BEED | 6462 | 6462 | 0 | 5 | BEED | 3853 | 3850 | -3
6 | BHANDARA | 12894 | 12921 | -27 | 6 | BHANDARA | 2620 | 2617 | -3
7 | BULDHANA | 9235 | 9264 | -29 | 7 | BULDHANA | 5330 | 5331 | 1
8 | CHANDRAPUR | 10083 | 10086 | -3 | 8 | CHANDRAPUR | 6386 | 6392 | 6
9 | DHULE | 24085 | 24121 | -36 | 9 | DHULE | 5292 | 5325 | 33
10 | GADCHIROLI | 6138 | 6145 | -7 | 10 | GADCHIROLI | 4468 | 4477 | 9
11 | GONDIA | 15400 | 15422 | -22 | 11 | GONDIA | 2462 | 2402 | -60
12 | HINGOLI | 4052 | 4054 | -2 | 12 | HINGOLI | 5336 | 5341 | 5
13 | JALGAON | 21284 | 21291 | -7 | 13 | JALGAON | 6326 | 6336 | 10
14 | JALNA | 4265 | 4269 | -4 | 14 | JALNA | 2186 | 2208 | 22
15 | KOLHAPUR | 6034 | 6034 | 0 | 15 | KOLHAPUR | 5049 | 5042 | -7
16 | LATUR | 4554 | 4554 | 0 | 16 | LATUR | 6898 | 6900 | 2
17 | NAGPUR | 8134 | 8138 | -4 | 17 | NAGPUR | 3319 | 3315 | -4
18 | NANDED | 11482 | 11526 | -44 | 18 | NANDED | 4946 | 4961 | 15
19 | NANDURBAR | 46692 | 46751 | -59 | 19 | NANDURBAR | 4270 | 4270 | 0
20 | NASHIK | 38352 | 38383 | -31 | 20 | NASHIK | 6337 | 6353 | 16
21 | OSMANABAD | 2482 | 2482 | 0 | 21 | OSMANABAD | 3313 | 3314 | 1
22 | PALGHAR | 14404 | 14415 | -11 | 22 | PALGHAR | 2879 | 2883 | 4
23 | PARBHANI | 2671 | 2671 | 0 | 23 | PARBHANI | 4372 | 4347 | -25
24 | PUNE | 6477 | 6478 | -1 | 24 | PUNE | 4742 | 4741 | -1
25 | RAIGAD | 4071 | 4071 | 0 | 25 | RAIGAD | 2337 | 2341 | 4
26 | RATNAGIRI | 2438 | 2440 | -2 | 26 | RATNAGIRI | 2301 | 2299 | -2
27 | SANGLI | 6207 | 6207 | 0 | 27 | SANGLI | 3122 | 3118 | -4
28 | SATARA | 5138 | 5142 | -4 | 28 | SATARA | 4036 | 4038 | 2
29 | SINDHUDURG | 1785 | 1787 | -2 | 29 | SINDHUDURG | 783 | 783 | 0
30 | SOLAPUR | 13742 | 13743 | -1 | 30 | SOLAPUR | 6768 | 6766 | -2
31 | THANE | 4388 | 4388 | 0 | 31 | THANE | 2143 | 2140 | -3
32 | WARDHA | 5046 | 5050 | -4 | 32 | WARDHA | 3897 | 3903 | 6
33 | WASHIM | 3568 | 3568 | 0 | 33 | WASHIM | 2538 | 2536 | -2
34 | YAVATMAL | 11757 | 11766 | -9 | 34 | YAVATMAL | 7515 | 7523 | 8
| Grand Total | 368271 | 368626 | -355 |  | Grand Total | 150282 | 150366 | 84

## Awaas Plus
AwaasPlus Aadhar Report
|  | Total Registered |  | Total Aadhar Seeded |  | % Seeded |  | Total Aadhar To Be Seeded
#SNo | District Name | Total HH registered | Total members registered | Total Aadhar seeded for HH till date | Total Aadhar seeded for Members till date | % HH | % MM | HH | MM
1 | AHMEDNAGAR | 293600 | 498771 | 283701 | 368282 | 96.6284 | 73.8379 | 9899 | 130489
2 | AKOLA | 93150 | 181944 | 79154 | 128107 | 84.9748 | 70.4101 | 13996 | 53837
3 | AMRAVATI | 174143 | 328889 | 137579 | 178613 | 79.0035 | 54.308 | 36564 | 150276
4 | AURANGABAD | 260947 | 390628 | 243101 | 243780 | 93.1611 | 62.4072 | 17846 | 146848
5 | BEED | 258662 | 336111 | 244490 | 184410 | 94.521 | 54.8658 | 14172 | 151701
6 | BHANDARA | 123736 | 175058 | 122171 | 164454 | 98.7352 | 93.9426 | 1565 | 10604
7 | BULDHANA | 236559 | 456667 | 215097 | 336978 | 90.9274 | 73.7907 | 21462 | 119689
8 | CHANDRAPUR | 157806 | 279879 | 139578 | 222428 | 88.4491 | 79.4729 | 18228 | 57451
9 | DHULE | 199567 | 264536 | 182966 | 144014 | 91.6815 | 54.4402 | 16601 | 120522
10 | GADCHIROLI | 102629 | 187479 | 93978 | 148276 | 91.5706 | 79.0894 | 8651 | 39203
11 | GONDIA | 143614 | 176674 | 142733 | 73711 | 99.3866 | 41.7215 | 881 | 102963
12 | HINGOLI | 124003 | 201515 | 115417 | 128603 | 93.076 | 63.8181 | 8586 | 72912
13 | JALGAON | 316732 | 506297 | 276816 | 299133 | 87.3975 | 59.0825 | 39916 | 207164
14 | JALNA | 221851 | 295766 | 188737 | 194940 | 85.0738 | 65.9102 | 33114 | 100826
15 | KOLHAPUR | 181903 | 460667 | 169821 | 332602 | 93.358 | 72.2001 | 12082 | 128065
16 | LATUR | 152079 | 271793 | 147434 | 218500 | 96.9457 | 80.3921 | 4645 | 53293
17 | NAGPUR | 91329 | 155183 | 86236 | 128656 | 94.4235 | 82.906 | 5093 | 26527
18 | NANDED | 351308 | 605305 | 321647 | 437876 | 91.557 | 72.3397 | 29661 | 167429
19 | NANDURBAR | 199231 | 216185 | 179157 | 157536 | 89.9243 | 72.8709 | 20074 | 58649
20 | NASHIK | 288171 | 477991 | 281126 | 166046 | 97.5553 | 34.7383 | 7045 | 311945
21 | OSMANABAD | 124374 | 213049 | 105630 | 135187 | 84.9293 | 63.4535 | 18744 | 77862
22 | PALGHAR | 112736 | 153743 | 106923 | 98546 | 94.8437 | 64.0979 | 5813 | 55197
23 | PARBHANI | 189536 | 333188 | 181275 | 247265 | 95.6415 | 74.2119 | 8261 | 85923
24 | PUNE | 113054 | 254648 | 103957 | 168843 | 91.9534 | 66.3045 | 9097 | 85805
25 | RAIGAD | 50390 | 119939 | 44906 | 83234 | 89.1169 | 69.3969 | 5484 | 36705
26 | RATNAGIRI | 78746 | 156593 | 73665 | 117087 | 93.5476 | 74.7715 | 5081 | 39506
27 | SANGLI | 132583 | 315040 | 126652 | 248173 | 95.5266 | 78.7751 | 5931 | 66867
28 | SATARA | 118101 | 207875 | 114032 | 179367 | 96.5546 | 86.286 | 4069 | 28508
29 | SINDHUDURG | 36729 | 92584 | 36372 | 87741 | 99.028 | 94.7691 | 357 | 4843
30 | SOLAPUR | 207486 | 374201 | 198483 | 249729 | 95.6609 | 66.7366 | 9003 | 124472
31 | THANE | 57329 | 110665 | 53539 | 41452 | 93.389 | 37.4572 | 3790 | 69213
32 | WARDHA | 75113 | 159617 | 74184 | 143775 | 98.7632 | 90.075 | 929 | 15842
33 | WASHIM | 143381 | 299263 | 137220 | 193718 | 95.7031 | 64.7317 | 6161 | 105545
34 | YAVATMAL | 349478 | 621314 | 271524 | 410726 | 77.6942 | 66.106 | 77954 | 210588
| Total | 5760056 | 9879057 | 5279301 | 6661788 | 91.6536 | 67.4334 | 480755 | 3217269
Thread was being aborted.

## PWL & Job card
Job card Mapping Aawas Plus Compare Report As On 18th Dec 2020 | [6 empty] | PWL aadhar seeding Compare Report As On 18th Dec
S.No | District Name | Total HH in Awaas+ | Total HH registered | Job Card Mapped As On 17th Dec | Job Card Mapped As On 18th Dec | Achievement | S.No | District Name | Total Beneficiaries | PWL Aadhar SEEDING As On 17th Dec | PWL Aadhar SEEDING As On 16th Dec | Achievement
1 | AHMEDNAGAR | 293600 | 49194 | 49186 | 49229 | 43 | 1 | AHMEDNAGAR | 55246 | 44498 | 44518 | 20
2 | AKOLA | 93150 | 41525 | 41511 | 41513 | 2 | 2 | AKOLA | 46939 | 38558 | 38560 | 2
3 | AMRAVATI | 174143 | 80053 | 79988 | 79990 | 2 | 3 | AMRAVATI | 92731 | 73070 | 73014 | -56
4 | AURANGABAD | 260947 | 22079 | 22056 | 22058 | 2 | 4 | AURANGABAD | 22745 | 20728 | 20728 | 0
5 | BEED | 258662 | 18812 | 18793 | 18793 | 0 | 5 | BEED | 19760 | 16988 | 16988 | 0
6 | BHANDARA | 123736 | 57460 | 57440 | 57443 | 3 | 6 | BHANDARA | 62999 | 53732 | 53734 | 2
7 | BULDHANA | 236559 | 28226 | 28217 | 28217 | 0 | 7 | BULDHANA | 29863 | 26844 | 26844 | 0
8 | CHANDRAPUR | 157806 | 30271 | 30269 | 30270 | 1 | 8 | CHANDRAPUR | 31975 | 29199 | 29207 | 8
9 | DHULE | 199567 | 45811 | 45801 | 45807 | 6 | 9 | DHULE | 50700 | 33459 | 33462 | 3
10 | GADCHIROLI | 102629 | 22102 | 22090 | 22079 | -11 | 10 | GADCHIROLI | 23260 | 19165 | 19154 | -11
11 | GONDIA | 143614 | 87833 | 87443 | 87477 | 34 | 11 | GONDIA | 92848 | 70638 | 70625 | -13
12 | HINGOLI | 124003 | 10493 | 10490 | 10490 | 0 | 12 | HINGOLI | 11280 | 10432 | 10432 | 0
13 | JALGAON | 316732 | 63526 | 63509 | 63527 | 18 | 13 | JALGAON | 72977 | 49276 | 49315 | 39
14 | JALNA | 221851 | 12355 | 12351 | 12352 | 1 | 14 | JALNA | 13384 | 7843 | 7845 | 2
15 | KOLHAPUR | 181903 | 15831 | 15829 | 15831 | 2 | 15 | KOLHAPUR | 16389 | 13435 | 13442 | 7
16 | LATUR | 152079 | 10283 | 10279 | 10279 | 0 | 16 | LATUR | 10968 | 9291 | 9291 | 0
17 | NAGPUR | 91329 | 42319 | 42317 | 42320 | 3 | 17 | NAGPUR | 44891 | 38683 | 38702 | 19
18 | NANDED | 351308 | 45214 | 45186 | 45203 | 17 | 18 | NANDED | 50470 | 26232 | 26310 | 78
19 | NANDURBAR | 199231 | 99172 | 99153 | 99162 | 9 | 19 | NANDURBAR | 106835 | 91770 | 91773 | 3
20 | NASHIK | 288171 | 69810 | 69796 | 69819 | 23 | 20 | NASHIK | 71791 | 66565 | 66586 | 21
21 | OSMANABAD | 124374 | 6039 | 6037 | 6037 | 0 | 21 | OSMANABAD | 6502 | 5656 | 5663 | 7
22 | PALGHAR | 112736 | 25846 | 25843 | 25843 | 0 | 22 | PALGHAR | 26349 | 16364 | 16364 | 0
23 | PARBHANI | 189536 | 6846 | 6843 | 6843 | 0 | 23 | PARBHANI | 7165 | 6618 | 6641 | 23
24 | PUNE | 113054 | 18569 | 18566 | 18578 | 12 | 24 | PUNE | 21460 | 15533 | 15549 | 16
25 | RAIGAD | 50390 | 8256 | 8255 | 8273 | 18 | 25 | RAIGAD | 9418 | 7596 | 7622 | 26
26 | RATNAGIRI | 78746 | 6897 | 6896 | 6897 | 1 | 26 | RATNAGIRI | 8039 | 6854 | 6855 | 1
27 | SANGLI | 132583 | 19337 | 19231 | 19231 | 0 | 27 | SANGLI | 21538 | 18002 | 18002 | 0
28 | SATARA | 118101 | 13874 | 13869 | 13869 | 0 | 28 | SATARA | 14089 | 13391 | 13391 | 0
29 | SINDHUDURG | 36729 | 4564 | 4564 | 4564 | 0 | 29 | SINDHUDURG | 4760 | 4418 | 4418 | 0
30 | SOLAPUR | 207486 | 47672 | 47626 | 47626 | 0 | 30 | SOLAPUR | 48036 | 41966 | 41966 | 0
31 | THANE | 57329 | 6614 | 6613 | 6613 | 0 | 31 | THANE | 7320 | 6490 | 6490 | 0
32 | WARDHA | 75113 | 16556 | 16556 | 16556 | 0 | 32 | WARDHA | 17513 | 16030 | 16030 | 0
33 | WASHIM | 143381 | 9789 | 9787 | 9787 | 0 | 33 | WASHIM | 10886 | 9423 | 9423 | 0
34 | YAVATMAL | 349478 | 39169 | 39087 | 39088 | 1 | 34 | YAVATMAL | 40699 | 38387 | 38387 | 0
| Total | 5760056 | 1082397 | 1081477 | 1081664 | 187 |  | Total | 1171825 | 947134 | 947331 | 197

## Ujjwala
Ujjwala Compare Report
SNo | District Name | Eligible for lpg connection As On 17th Dec | Eligible for lpg connection As On 18th Dec | Achievement | House with lpg connection As On 17th Dec | House with lpg connection As On 18th Dec | Achievement
1 | AHMEDNAGAR | 23916 | 23926 | 10 | 5809 | 5809 | 0
2 | AKOLA | 22078 | 22080 | 2 | 3555 | 3555 | 0
3 | AMRAVATI | 41731 | 41752 | 21 | 5610 | 5610 | 0
4 | AURANGABAD | 11851 | 11856 | 5 | 2090 | 2090 | 0
5 | BEED | 9214 | 9214 | 0 | 1839 | 1839 | 0
6 | BHANDARA | 23302 | 23317 | 15 | 3121 | 3121 | 0
7 | BULDHANA | 15434 | 15442 | 8 | 2716 | 2716 | 0
8 | CHANDRAPUR | 17132 | 17133 | 1 | 1869 | 1869 | 0
9 | DHULE | 32812 | 32833 | 21 | 4087 | 4087 | 0
10 | GADCHIROLI | 12445 | 12457 | 12 | 962 | 962 | 0
11 | GONDIA | 29959 | 29994 | 35 | 4055 | 4055 | 0
12 | HINGOLI | 6124 | 6128 | 4 | 1120 | 1120 | 0
13 | JALGAON | 30364 | 30370 | 6 | 4698 | 4698 | 0
14 | JALNA | 6410 | 6417 | 7 | 1551 | 1551 | 0
15 | KOLHAPUR | 8105 | 8108 | 3 | 2084 | 2084 | 0
16 | LATUR | 6520 | 6520 | 0 | 1332 | 1332 | 0
17 | NAGPUR | 15857 | 15866 | 9 | 1968 | 1968 | 0
18 | NANDED | 19088 | 19103 | 15 | 3820 | 3820 | 0
19 | NANDURBAR | 76390 | 76428 | 38 | 2956 | 2956 | 0
20 | NASHIK | 52128 | 52160 | 32 | 6956 | 6956 | 0
21 | OSMANABAD | 3193 | 3193 | 0 | 783 | 783 | 0
22 | PALGHAR | 22572 | 22580 | 8 | 2061 | 2061 | 0
23 | PARBHANI | 4005 | 4005 | 0 | 931 | 931 | 0
24 | PUNE | 9580 | 9581 | 1 | 1522 | 1522 | 0
25 | RAIGAD | 6000 | 6000 | 0 | 396 | 396 | 0
26 | RATNAGIRI | 3986 | 3986 | 0 | 879 | 879 | 0
27 | SANGLI | 9010 | 9012 | 2 | 1929 | 1929 | 0
28 | SATARA | 6722 | 6724 | 2 | 1938 | 1938 | 0
29 | SINDHUDURG | 2576 | 2576 | 0 | 433 | 433 | 0
30 | SOLAPUR | 19785 | 19785 | 0 | 4935 | 4935 | 0
31 | THANE | 5805 | 5805 | 0 | 249 | 249 | 0
32 | WARDHA | 8275 | 8279 | 4 | 1732 | 1732 | 0
33 | WASHIM | 5498 | 5498 | 0 | 1086 | 1086 | 0
34 | YAVATMAL | 21636 | 21641 | 5 | 3767 | 3767 | 0
| Total | 589503 | 589769 | 266 | 84839 | 84839 | 0

## Mgnrega
MGNREGA Compare Report As On 17th Dec
Sr.No | District | Total Mandays As On 16th Dec | Total Mandays As On 17th Dec | Achivement
1 | AHMEDNAGAR | 33769 | 33795 | 26
2 | AKOLA | 28203 | 28210 | 7
3 | AMRAVATI | 52559 | 52578 | 19
4 | AURANGABAD | 20014 | 20021 | 7
5 | BEED | 13025 | 13025 | 0
6 | BHANDARA | 36173 | 36238 | 65
7 | BULDHANA | 27252 | 27253 | 1
8 | CHANDRAPUR | 31015 | 31036 | 21
9 | DHULE | 40252 | 40274 | 22
10 | GADCHIROLI | 20881 | 20890 | 9
11 | GONDIA | 39622 | 39687 | 65
12 | HINGOLI | 6910 | 6910 | 0
13 | JALGAON | 38084 | 38099 | 15
14 | JALNA | 4276 | 4280 | 4
15 | KOLHAPUR | 11511 | 11511 | 0
16 | LATUR | 16843 | 16849 | 6
17 | NAGPUR | 20501 | 20514 | 13
18 | NANDED | 21452 | 21453 | 1
19 | NANDURBAR | 84948 | 84958 | 10
20 | NASHIK | 67544 | 67556 | 12
21 | OSMANABAD | 8593 | 8593 | 0
22 | PALGHAR | 22252 | 22258 | 6
23 | PARBHANI | 8856 | 8858 | 2
24 | PUNE | 14001 | 14004 | 3
25 | RAIGAD | 1715 | 1715 | 0
26 | RATNAGIRI | 6796 | 6801 | 5
27 | SANGLI | 10493 | 10494 | 1
28 | SATARA | 12577 | 12579 | 2
29 | SINDHUDURG | 1341 | 1342 | 1
30 | SOLAPUR | 14713 | 14713 | 0
31 | THANE | 7467 | 7467 | 0
32 | WARDHA | 14633 | 14645 | 12
33 | WASHIM | 13755 | 13763 | 8
34 | YAVATMAL | 36251 | 36271 | 20
| Total | 788277 | 788640 | 363

## Compared report
Cummulative PMAY-G Online Progress Report From 15th Nov To 14th Dec 2020 | [8 empty] | State scheme
SNo | District Name | Target PMAYG | Sanction |  | 1st installment |  | Complation |  | State scheme | Sanction |  | 1st installment |  | Complation |  | Total Progress
|  |  | Progress on 14/12/2020 | Remaining | Progress on 14/12/2020 | Remaining | Progress on 14/12/2020 | Remaining | Target States Scheme | Progress on 14/12/2020 | Remaining Sanction | Progress on 14/12/2020 | Yet to give 1st Inst | Progress on 14/12/2020 | Incomplet
1 | BEED | 20320 | -3 | 6382 | 0 | 2775 | 8 | 11424 | 13236 | 2 | 4206 | 0 | 347 | 1 | 6605 | 842
2 | BHANDARA | 63597 | 0 | 27124 | 0 | 8039 | 53 | 43584 | 15386 | 0 | 1071 | 0 | 1738 | 3 | 8231 | 585
3 | NAGPUR | 45792 | 188 | 14970 | 0 | 11315 | 19 | 31206 | 9482 | 0 | 350 | 0 | 1110 | 2 | 2964 | 578
4 | JALGAON | 75723 | 0 | 28442 | 0 | 10151 | 5 | 46662 | 17383 | 38 | 1288 | 0 | 3831 | 0 | 8409 | 404
5 | GONDIA | 92862 | 1128 | 23431 | 0 | 28467 | 19 | 68038 | 13480 | 0 | 4121 | 0 | 1430 | 3 | 8512 | 182
6 | KOLHAPUR | 17047 | 0 | 4394 | 0 | 2933 | 33 | 9162 | 10935 | 0 | 99 | 0 | 1945 | 7 | 3134 | 171
7 | PUNE | 21818 | 0 | 9083 | 0 | 1226 | 1 | 12979 | 10457 | 7 | 1730 | 0 | 658 | 1 | 4115 | 168
8 | NASHIK | 72630 | 13 | 5447 | 0 | 7592 | 92 | 24447 | 19111 | 0 | 1209 | 0 | 3382 | 15 | 9992 | 143
9 | SATARA | 14166 | 3 | 3146 | 0 | 3543 | 12 | 7901 | 9559 | 0 | 54 | 0 | 1796 | 0 | 2859 | 128
10 | NANDURBAR | 111956 | 0 | 13694 | 0 | 8909 | 17 | 49734 | 10307 | 0 | 476 | 0 | 640 | 0 | 4201 | 105
11 | PALGHAR | 26966 | -15 | 1298 | 0 | 919 | 50 | 6237 | 6455 | 0 | 649 | 0 | 316 | 8 | 2545 | 93
12 | RAIGAD | 9566 | 0 | 2286 | 0 | 669 | 6 | 3702 | 3833 | 0 | 30 | 0 | 414 | 9 | 867 | 84
13 | DHULE | 52614 | 98 | 8292 | 0 | 7062 | 56 | 22695 | 12351 | 0 | 434 | 0 | 1282 | 22 | 4587 | 78
14 | NANDED | 50791 | 0 | 10791 | 0 | 13767 | 52 | 32890 | 17863 | 0 | 7807 | 0 | 946 | 21 | 11986 | 73
15 | SOLAPUR | 49500 | 18 | 17311 | 0 | 9655 | 14 | 30925 | 15433 | 0 | 389 | 0 | 2260 | 0 | 4382 | 71
16 | AMRAVATI | 93272 | 0 | 39183 | 0 | 5966 | 25 | 55196 | 14486 | 0 | 594 | 0 | 3176 | 9 | 6380 | 63
17 | CHANDRAPUR | 32694 | 257 | 5257 | 0 | 7767 | 11 | 16918 | 24728 | 0 | 8154 | 0 | 1312 | 15 | 16839 | 49
18 | AHMEDNAGAR | 56134 | 0 | 20508 | 0 | 5901 | 26 | 35023 | 30450 | 15 | 2409 | 0 | 4498 | 3 | 14728 | 44
19 | OSMANABAD | 6632 | 0 | 1723 | 0 | 1132 | 0 | 3487 | 15251 | 9 | 6864 | 0 | 2388 | 0 | 10844 | 35
20 | YAVATMAL | 41521 | 30 | 9755 | 0 | 6624 | 6 | 21707 | 19265 | 0 | 319 | 0 | 2472 | 22 | 9670 | 28
21 | AKOLA | 47181 | 0 | 15626 | 0 | 5215 | 15 | 27405 | 14198 | 0 | 801 | 0 | 4184 | 7 | 8310 | 22
22 | BULDHANA | 30604 | 10 | 10896 | 0 | 2043 | 14 | 16295 | 12190 | 0 | 195 | 0 | 2792 | 2 | 4512 | 16
23 | AURANGABAD | 23273 | 0 | 1643 | 0 | 7601 | 4 | 12334 | 17770 | 0 | 1324 | 0 | 7939 | 10 | 11683 | 14
24 | WARDHA | 17575 | 147 | 7255 | 0 | 984 | 4 | 9935 | 8310 | 0 | 13 | 0 | 542 | 4 | 3635 | 8
25 | RATNAGIRI | 8100 | 18 | 2016 | 0 | 1889 | 3 | 4252 | 5864 | 4 | 8 | 0 | 358 | 0 | 1318 | 7
26 | WASHIM | 11091 | 0 | 4579 | 0 | 116 | 3 | 5864 | 7712 | 0 | 14 | 0 | 2180 | 2 | 3864 | 5
27 | HINGOLI | 11335 | 479 | 3352 | 0 | 791 | 3 | 5368 | 9745 | 0 | 1380 | 0 | 635 | 1 | 3575 | 4
28 | JALNA | 13465 | 2 | 5274 | 0 | 655 | 0 | 7488 | 7135 | 0 | 2012 | 0 | 178 | 3 | 3928 | 3
29 | PARBHANI | 7603 | 0 | 1194 | 0 | 1649 | 0 | 3688 | 14543 | 0 | 2253 | 0 | 1372 | 2 | 5466 | 2
30 | GADCHIROLI | 23746 | 29 | 3326 | 0 | 4404 | 4 | 12669 | 11477 | 0 | 1372 | 0 | 1377 | 6 | 6181 | 1
31 | SANGLI | 22172 | 0 | 10023 | 0 | 877 | 0 | 13423 | 7082 | 0 | 853 | 0 | 918 | 1 | 2479 | 1
32 | SINDHUDURG | 4947 | 270 | 1804 | 0 | 251 | 0 | 2427 | 1851 | 0 | 17 | 0 | 308 | 1 | 402 | 1
33 | THANE | 7395 | 0 | 912 | 0 | 263 | 0 | 1909 | 3524 | 0 | 260 | 0 | 27 | 1 | 834 | 1
34 | LATUR | 11302 | 0 | 3807 | 0 | 260 | 0 | 4936 | 19992 | 0 | 3988 | 0 | 2615 | 0 | 9536 | 0
| Total | 1195390 | 2672 | 383066 | 5454 | 117737 | 5544 | 664859 | 430844 | 75 | 56743 | 0 | 61366 | 181 | 207573